## Sheet1
SUMMARY OF MAJOR ROAD PROJECTS PROGRAMMED BY LEE COUNTY - FY 15/16 TO FY 19/20 (as adopted September 15, 2015)
[5 empty] | FY 98-14 | [9 empty] | FUTURE
COMM | PROJ. |  |  | LENGTH | PRIOR | FY 14/15 | [5 empty] | 5-YEAR |  | PROJECT | REVENUE | PROJECT
DIST. | # | PROJECT NAME | DRIVER | (MILES) | EXP. | BUDGET | 15/16 | 16/17 | 17/18 | 18/19 | 19/20 | TOTAL | 6-10 | TOTAL | SOURCE | MANAGER
MAJOR PROJECTS
2 | 205075 | Alico Rd 4L/Ben Hill-Airport Haul Rd (DESIGN UNDERWAY) | Added capacity for | 1.78 | 722013 | 1672579 | 0 | 0 | 11500000 | 540000 | 0 | 12040000 | 0 | 14434592 | GT/IF25/ | Sarah Clarke, 533-8718
|  | 4L widening, including on-road bike lanes and 12' multi-use paths | future RED developments |  | PRELIM/DES | DES/MIT |  |  | CST/CEI | LS |  |  |  |  | AV | sclarke@leegov.com
|  | on both sides | NM - Discretionary/
|  | PER BOCC ACTION 11/19/13 TO SCHEDULE CST/CEI PHASES IN FY 17/18, THE | Deferrable
FOLLOWING STATEMENT WAS INCLUDED: "THESE PHASES COULD BE
ADVANCED IN THE FUTURE AT BOARD DISCRETION SHOULD CONDITIONS
WARRANT TO SUPPORT ECONOMIC DEVELOPMENT INITIATIVES, AND IF
FUNDING IS AVAILABLE THROUGH GOVERNMENT SOURCES OR PRIVATE
DEVELOPMENT SOURCES."
2,5 |  | Alico Rd. Connector/Alico Rd. to SR 82 opposite Sunshine Blvd. | People-to-jobs link, | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2240868 | 2240868 | 64000000 | 66240868 | IF25 | Sarah Clarke, 533-8718
|  | Funds to purchase ROW through Florida Rock property prior to 12/31/2020 per | Daniels Pkwy. relief | [7 empty] | ROW |  | ALL |  |  | sclarke@leegov.com
|  | purchase option agreement | NM - Core Critical
All | 206002 | Bicycle/Pedestrian Facilities | Implementation of bike- |  | 18607940 | 1410905 | 394000 | 2437000 | 1312000 | 843000 | 1161000 | 6147000 | 3700000 | 29865845 | IF/GT | Sarah Clarke, 533-8718
|  | Annual project for facilities on existing County-maintained roads | ped plan, BPAC prior- |  | DES/CST | DES/CST | DES/CST | DES/CST | DES/CST | DES/CST | DES/CST |  | CST |  |  | sclarke@leegov.com
ities, Complete Streets
|  | Specific Projects: | principals
1 |  | Gulf Blvd. Path Widening, Wheeler Rd-1st St. W. | NM - Core Critical |  |  |  | 24000 | 104000 |  |  |  | 128000 |  | 128000 | IF21
[7 empty] | DES/SUR | CST/CEI
2 |  | Fiddlesticks Blvd.Bike Path/Resurface, Fiddlesticks Ent.-Daniels |  |  |  | 770000 | [5 empty] | 0 |  | 770000 | GT/IF24
CST
2 |  | Winkler Rd. Sidewalk/East Side, College Pkwy. to McGregor Blvd. |  |  |  |  | 97000 | 561000 |  |  |  | 658000 |  | 658000 | GT
[7 empty] | DES/SUR | CST/CEI
4 |  | Hancock Bridge Pkwy. Sidewalk/North Side, Moody Rd. to US 41 |  |  |  |  | 76000 | 438000 |  |  |  | 514000 |  | 514000 | GT
[7 empty] | DES/SUR | CST/CEI
4 |  | Mariana Ave. Sidewalk/South Side, US 41 to Bus. 41 |  |  |  |  | 197000 | 1145000 |  |  |  | 1342000 |  | 1342000 | IF22
[7 empty] | DES/SUR | CST/CEI
4 |  | Hancock Bridge Pkwy. Sidewalk/North Side, NE 16th Pl. to SE 24th Ave. | [5 empty] | 124000 | 866000 |  |  | 990000 |  | 990000 | GT
[8 empty] | DES/SUR | CST/CEI
2 |  | Boy Scout Dr. Pedestrian Safety Improvements, Summerlin Rd. to US 41 | [5 empty] | 35000 | 202000 |  |  | 237000 |  | 237000 | GT
[8 empty] | DES/SUR | CST/CEI
2 |  | Beacon Manor Dr. Sidewalk, US 41 to S. Danley Dr. | [5 empty] | 30000 | 139000 |  |  | 169000 |  | 169000 | IF23
[8 empty] | DES/SUR | CST/CEI
5 |  | E. 12th St. Sidewalk/North Side, Gerald Ave. to Joel Blvd. | [6 empty] | 11000 | 40000 |  | 51000 |  | 51000 | IF23
[9 empty] | DES/SUR | CST/CEI
1 |  | Stringfellow Rd. Shared Use Path/East Side, Sanibel Blvd. to York Rd. | [6 empty] | 46000 | 290000 |  | 336000 |  | 336000 | GT
[9 empty] | DES/SUR | CST/CEI
4 |  | Hart Rd. Shared Use Path/West Side, SR 78 to Forest Park Dr. | [6 empty] | 48000 | 313000 |  | 361000 |  | 361000 | GT
[9 empty] | DES/SUR | CST/CEI
5 |  | Tice St. Sidewalk/South Side, Lynneda Ave. to Ortiz Ave. | [7 empty] | 63000 | 365000 | 428000 |  | 428000 | IF23
[10 empty] | DES/SUR | CST/CEI
5 |  | Tice St. Sidewalk/South Side, Ortiz Ave. to Lexington Ave. | [7 empty] | 96000 | 559000 | 655000 |  | 655000 | IF23
[10 empty] | DES/SUR | CST/CEI
2 |  | Alico Rd. Sidewalk/North Side, RR Crossing to Quaker Ln. | [7 empty] | 41000 | 237000 | 278000 |  | 278000 | IF24
[10 empty] | DES/SUR | CST/CEI
3 | 205724 | Big Carlos Pass Bridge Replacement | Bridge life cycle/con- |  | 0 | 5000000 | 3500000 | 3500000 | 3500000 | 3500000 | 1000000 | 15000000 | 25300000 | 45300000 | SANIBEL | Ehab Guirguis, 533-9400
|  | Funds to replace 2L bascule bridge, fixed-span bridge an option | dition |  |  | PD&E/CST | CST | CST | DES | CST | CST |  | CST/CEI |  | SURP. | eguirguis@leegov.com
|  |  | Mandated | [11 empty] | TOLLS
3 |  | Big Hickory Pass Bridge Replacement | Bridge life cycle/con- |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10043000 | 10043000 | SANIBEL | Ehab Guirguis, 533-9400
|  | Funds to replace 2L fixed-span bridge on Hickory Boulevard | dition | [9 empty] | CST/CEI |  | SURP. | eguirguis@leegov.com
|  | DESIGN FUNDING IN NEW PASS BRIDGE REPLACEMENT PROJECT ALONG | Mandated | [11 empty] | TOLLS/
|  | WITH DESIGN FOR LITTLE CARLOS PASS BRIDGE REPLACEMENT PROJECT | [12 empty] | GT
3 | 205723 | Bonita Beach Road Phase III (DES COMPLETE) | LOS, cost-sharing inter- | 2 | 1994332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23700000 | 25694332 | IF24/CITY/ | Sarah Clarke, 533-8718
|  | 6L widening, W. of US 41 to Old 41 - including on-road bike lanes and | local with City |  | DES | [7 empty] | ROW/CST |  | AV | sclarke@leegov.com
|  | sidewalks on both sides, and approx. 14 transit stops | Mandated
TO BE JOINTLY FUNDED WITH CITY PER INTERLOCAL AGREEMENT, RECENT
CITY COUNCIL ACTION DELETED CITY'S SHARE OF FUTURE FUNDING FROM
IT'S CIP AND PLANS, CITY DOING A CORRIDOR VISIONING STUDY
1,4 | 204088 | Burnt Store Road 4L (DES/ROW UNDERWAY) | Future growth, safety, | 4.3 | 9571084 | 14689311 | 6580000 | 5042246 | 897754 | 8700000 | 630000 | 21850000 | 0 | 46110395 | CAPE/MP | Sarah Clarke, 533-8718
|  | SR 78 (Pine Island Road) to Van Buren Parkway (IN SEGMENTS) | City priority and shared |  | DES/ROW | DES/ROW/ | DES/ROW/ | CST/CEI | CST/LS | CST/CEI | LS |  |  |  | SURP. | sclarke@leegov.com
|  | - including on-road bike lanes, 10' multi-use path on east side, 6' side | funding via surplus tolls |  |  | CST/CEI | LS | Central Seg. |  | South Seg. |  |  |  |  | TOLLS/
|  | walk on west side | NM - Essential |  |  | North Seg. | [8 empty] | IF22/TRIP/
|  | PER BOCC ACTION 11/19/13, CONSTRUCTION STARTING WITH NORTH | [12 empty] | AV
SEGMENT (DIPLOMAT PKWY. TO VAN BUREN PKWY.)
1,2 |  | Cape Coral Bridge WB Span Replacement | Age/condition, escalating |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 4000000 | 5000000 | 82500000 | 87500000 | CAPE/MP | Ehab Guirguis, 533-9400
|  | Accumulation of Cape and Midpoint surplus toll funds toward replacement of | maintenance costs | [6 empty] | DES | DES |  |  |  | SURP. | eguirguis@leegov.com
|  | westbound span of Cape Coral Bridge by approximately 2028 | Mandated | [11 empty] | TOLLS
FUNDING FOR DES PHASE SPREAD OVER 2 YEARS, SUFFICIENT FUNDING
TO PROCEED IN FY 19/20
2 |  | Colonial Blvd. Alternatives Analysis | LOS F per Concurrency |  | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 350000 | 0 | 350000 | IF23 | Sarah Clarke, 533-8718
|  | Funds to evaluate improvement options between McGregor Blvd. and US 41 | report | [12 empty] | sclarke@leegov.com
NM - Essential
4 | 205082 | Corbett Rd. Widening/Resurfacing | Substandard condition, |  | 0 | 150000 | 690000 | 0 | 0 | 0 | 0 | 690000 | 0 | 840000 | GT | Sarah Clarke, 533-8718
|  | Diplomat Pkwy. to Littleton Rd - Widen pavement for 11-ft lanes, including | Federal facilities in City |  |  | DES | CST | [8 empty] | sclarke@leegov.com
|  | 8-ft off-road path on west side | NM - Essential
2 |  | Crystal Dr. 2LD | Complete Streets prin- |  | 0 | 0 | 0 | 0 | 0 | 850000 | 850000 | 1700000 | 5750000 | 7450000 | IF23 | Sarah Clarke, 533-8718
|  | US 41 to Metro Pkwy. - Reconstruct 2L undivided roadway to 2L divided | cipals, combined with | [6 empty] | DES | ROW |  | CST/CEI |  |  | sclarke@leegov.com
|  | section with on-road bike lanes and sidewalks on both sides | resurfacing need
NM - Core Critical
2 | 205077 | Crystal/Plantation Roundabout (ROW UNDERWAY) | Intersection control |  | 1125 | 560339 | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 586464 | GT/AV | Sarah Clarke, 533-8718
|  | Construct roundabout at intersection, including bike-ped features | needed, signal alternative |  | SUR | ROW/CST | LS | [8 empty] | sclarke@leegov.com
NM - Core Critical
3 | 205067 | Estero Blvd. Improvements (SEGMENT 1 DES UNDERWAY, CST THIS YEAR) | Town request, reflective | 6 | 2612258 | 9169621 | 7000000 | 750000 | 7300000 | 750000 | 7000000 | 22800000 | 15500000 | 50081879 | GT/IF24/ | Rob Phelan, 533-8594
|  | Phased reconstruction of County roadway within Town, including adding | of Town's Streetscape |  | PRELIM/DES | DES/CST/CEI | CST/CEI | DES | CST/CEI/LS | DES | CST/CEI |  | DES/CST/CEI |  | AV | rphelan@leegov.com
|  | trolley stops, bike lanes and sidewalks on both sides, and replacement | Master Plan, Complete |  | CST
|  | of City water lines and County sewer lines (costs don't reflect utility | Streets principals |  |  | Segment 1 CST | Segment 2 | Segment 3 | Segment 3 | Segment 4 | Segment 4 |  | Segments 5
|  | replacements). | NM - Essential |  |  | Segment 2 DES | [6 empty] | and 6
PER BOCC ACTION 11/19/13, CONSTRUCTION WILL MOVE IN
CONSECUTIVE SEGMENTS FROM NORTH TO SOUTH STARTING AT
CRESCENT ST., WITH CST FUNDING EVERY OTHER YEAR.
IMPROVEMENT AT FOOT OF MATANZAS PASS BRIDGE NOT YET
IDENTIFIED AND FUNDED, TO BE EVALUATED IN FDOT PD&E STUDY.
5 |  | Gunnery Rd./8th St. Intersection Improvements | Intersection control |  | 200000 | 0 | 60000 | 850000 | 0 | 0 | 0 | 910000 | 0 | 1110000 | GT | Sarah Clarke, 533-8718
|  | Signalization and turn lane improvements | needed |  | DES |  | ROW | CST | [7 empty] | sclarke@leegov.com
NM- Core Critical
5 | 205063 | Homestead 4L/Sunrise-Alabama (ROW UNDERWAY) | LOS, community interest | 2.25 | 2362189 | 6375668 | 11605000 | 690000 | 0 | 0 | 0 | 12295000 | 0 | 21032857 | IF23/GT/ | Sarah Clarke, 533-8718
|  | 4L widening, south of Sunrise Blvd. to Alabama Rd., including on-road | Mandated |  | DES/ROW | DES/ROW/ | CST/CEI | LS | [6 empty] | AV | sclarke@leegov.com
|  | bike lanes and sidewalks on both sides |  |  |  | CST
5 | 205080 | Homestead Road Complete Street | Community planning re- | 1 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | GT | Sarah Clarke, 533-8718
|  | Reconstruction of existing 4LD roadway from Alabama Rd. to Beth Stacey | quest, Complete Streets |  |  | DES | [9 empty] | sclarke@leegov.com
|  | Blvd. to reflect community plan concept of Complete Street (still being | NM - Discretionary/
|  | defined in on-going planning/feasibility study) | Deferrable
4 |  | Kismet/Littleton Realignment | System continuity, City |  | 0 | 0 | 0 | 137500 | 675000 | 825000 | 0 | 1637500 | 0 | 1637500 | IF22 | Sarah Clarke, 533-8718
|  | Realignment of eastern end of Kismet Pkwy. to connect directly to | request, fund-sharing |  |  |  |  | DES | ROW | CST/CEI | [5 empty] | sclarke@leegov.com
|  | Littleton Rd., including on-road bike lanes and sidewalks on both sides | interlocal (if executed)
|  | (subject to execution of joint-funding interlocal agreement, amounts | NM - Essential
reflect County's share only, assumes 50/50 split of each phase)
5 |  | Lee Blvd./Gunnery Rd. Intersection Improvements | Congestion relief |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000 | GT | Sarah Clarke, 533-8718
|  | Initial study to define appropriate improvements consistent with Activity Center plans | NM- Core Critical |  |  |  | DES | [8 empty] | sclarke@leegov.com
3 |  | Little Carlos Pass Bridge Replacement | Bridge life cycle/con- |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3270000 | 3270000 | SANIBEL | Ehab Guirguis, 533-9400
|  | Replacement of existing 2-lane fixed span bridge on Hickory Boulevard | dition | [9 empty] | CST/CEI |  | SURP. | eguirguis@leegov.com
|  | DESIGN FUNDING IN NEW PASS BRIDGE REPLACEMENT PROJECT ALONG | Mandated | [11 empty] | TOLLS/
|  | WITH DESIGN FOR BIG HICKORY PASS BRIDGE REPLACEMENT PROJECT | [12 empty] | GT
1 |  | Little Pine Island Pass Bridge Replacement | Bridge life cycle/con- |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3385000 | 3385000 | GT | Ehab Guirguis, 533-9400
|  | Replacement of existing 2-lane fixed span bridge on Pine Island Road | dition | [9 empty] | DES/CST/CEI |  |  | eguirguis@leegov.com
Mandated
5 | 205068 | Luckett Rd 4L/Ortiz to I-75 (ROW UNDERWAY) | Linkage between I-75 | 0.46 | 550792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3519000 | 4069792 | IF23/AV | Rob Phelan, 533-8594
|  | 4L widening, including on-road bike lanes and sidewalks on both sides | and parallel reliever |  | ROW | [7 empty] | CST/CEI/LS |  |  | rphelan@leegov.com
NM - Essential
3 |  | New Pass Bridge Replacement | Bridge life cycle/con- |  | 0 | 0 | 0 | 0 | 2700000 | 5000000 | 5000000 | 12700000 | 7060000 | 19760000 | SANIBEL | Ehab Guirguis, 533-9400
|  | Replacement of existing 2-lane fixed span bridge on Hickory Boulevard | dition | [5 empty] | DES | CST | CST |  | CST/CEI |  | SURP. | eguirguis@leegov.com
|  | DESIGN FUNDING INCLUDES LITTLE CARLOS PASS BRIDGE AND | Mandated | [11 empty] | TOLLS/
|  | BIG HICKORY PASS BRIDGE REPLACEMENT PROJECTS, MAY SEEK | [12 empty] | GT
FINANCING TO FUND CONSTRUCTION OF ALL 3 TOGETHER
2 | 204100 | North Airport Rd. Ext. West (DES UNDERWAY) | Reliever to congested | 0.62 | 447778 | 4472177 | 70000 | 0 | 0 | 0 | 0 | 70000 | 0 | 4989955 | GF/IF23 | Sarah Clarke, 533-8718
|  | 2L Extension, end of existing road to Metro Parkway, including on-road | Colonial Blvd., develop- |  | DES/ROW | DES/RR/CST/ | CEI | [8 empty] | sclarke@leegov.com
|  | bike lanes, a 10' multi-use path on north side and 6' sidewalk on south | ment agreement |  |  | CEI
Mandated
2,4 |  | Ortiz 4L/Colonial-MLK | Parallel reliever to I-75, | 1.73 | 0 | 0 | 0 | 0 | 1550000 | 0 | 0 | 1550000 | 13269000 | 14819000 | IF23/AV | Rob Phelan, 533-8594
|  | 4L widening, Colonial Blvd. to SR 82 (Dr. Martin Luther King, Jr. Blvd.), | access to jail and EMS, | [5 empty] | DES |  |  |  | CST/CEI/MIT |  |  | rphelan@leegov.com
|  | including on-road bike lanes and sidewalks on both sides | projected LOS | [9 empty] | LS
NM - Essential
5 | 205056 | Ortiz 4L/Luckett-SR 80 | Parallel reliever to I-75, | 1.33 | 8414636 | 3143703 | 0 | 0 | 0 | 0 | 0 | 0 | 12450000 | 24008339 | IF23/AV | Rob Phelan, 533-8594
|  | 4L widening, Luckett Rd. to SR 80 (Palm Beach Blvd.), including on-road | projected LOS |  | DES/ROW | ROW | [6 empty] | CST/CEI/LS |  |  | rphelan@leegov.com
|  | bike lanes and sidewalks on both sides - Redesign anticipated to address | NM - Essential
REDESIGN ANTICIPATED TO ADDRESS COMMUNITY PLAN EMPHASIS ON
WALKABILITY, COMMUNITY WANTS TO LIMIT PROJECT TO 2LD
4,5 | 204072 | Ortiz 4L/MLK-Luckett | Parallel reliever to I-75, | 1.25 | 9200870 | 604812 | 0 | 0 | 0 | 0 | 0 | 0 | 9325000 | 19130682 | IF23/AV | Rob Phelan, 533-8594
|  | 4L widening, SR 82 (Dr. Martin Luther King, Jr. Blvd.) to Luckett Rd., | projected LOS |  | DES/ROW | ROW | [6 empty] | CST/CEI/LS |  |  | rphelan@leegov.com
|  | including on-road bike lanes and sidewalks on both sides | NM - Essential
2 | 205081 | Palomino Lane Improvements | Improved traffic flow, bike- | 1.5 | 0 | 169636 | 80364 | 1700000 | 0 | 0 | 0 | 1780364 | 0 | 1950000 | CITY IF/GT | Rob Phelan, 533-8594
|  | Addition of 8-foot off-road path on one side and left turn lanes at certain | ped safety, community |  |  | DES | DES | CST/CEI | [7 empty] | rphelan@leegov.com
|  | key locations, Daniels Pkwy. to Penzance Blvd. Future road impact fees | request
|  | provided by City per annexation interlocal to be earmarked for project. | NM - Essential
ALL | 206759 | Signal System ATMS Upgrade | Maximizes efficient use |  | 2068117 | 955925 | 750000 | 750000 | 750000 | 750000 | 750000 | 3750000 | 0 | 6774042 | GT | Rob Price, 533-9500
|  | Upgrade signal system and TOC equipment, install ITS field equipment to | of existing capacity |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | rprice@leegov.com
|  | support ATMS operations on County roads | NM - Core Critical
5 |  | Sunshine Blvd./8th St. W. Roundabout | Intersection control |  | 0 | 0 | 0 | 0 | 200000 | 200000 | 550000 | 950000 | 0 | 950000 | GT | Sarah Clarke, 533-8718
|  | Construct roundabout at intersection | needed, signal alternative | [5 empty] | DES | ROW | CST |  |  |  |  | sclarke@leegov.com
NM- Core Critical
2 | 204053 | Three Oaks Parkway Extension North | Extends major arterial, | 3.5 | 6936638 | 5690477 | 0 | 0 | 3000000 | 0 | 3000000 | 6000000 | 37250000 | 55877115 | IF24 | Sarah Clarke, 533-8718
|  | New 4L, N. of Alico Rd. to Daniels Pkwy., including on-road bike lanes | parallel reliever to I-75 |  | DES/ROW | DES/ROW |  |  | ROW |  | ROW |  | ROW/CST/CEI |  |  | sclarke@leegov.com
|  | and sidewalks on both sides | NM - Essential
1,2,3 | 205818 | Toll Interoperability | Age of equipment, rapid |  | 0 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 750000 | 0 | 900000 | SURP. | Sue Hopwood, 533-0157
|  | Funds for hardware/software changes to maintain interoperability with other toll | technology changes |  |  | CST | CST | CST | CST | CST | CST |  |  |  | TOLLS | shopwood@leegov.com
|  | agencies | NM - Core Critical
1,2,3 |  | Toll System Replacement | Age of equipment, rapid |  | 0 | 0 | 0 | 2250000 | 2250000 | 0 | 0 | 4500000 | 0 | 4500000 | SURP. | Sue Hopwood, 533-0157
|  | Funds for complete replacement due to technology changes | technology changes |  |  |  |  | CST | CST | [5 empty] | TOLLS | shopwood@leegov.com
NM - Core Critical
|  | SUBTOTALS |  | 36.72 | 63689772 | 55715153 | 31601364 | 19401746 | 35784754 | 23617000 | 27255868 | 137660732 | 320021000 | 577364618
MAJOR MAINTENANCE PROJECTS
CW | 404683 | Road Resurface/Rebuild Program | Pavement rating system, |  | 53734251 | 6475168 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 25000000 | 0 | 85209419 | GT | Dirk Danley, 533-9300
|  | Funds for rebuilding/resurfacing County-maintained roads as identified | complaints, asset prot. |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | ddanley@leegov.com
|  | under systematic evaluation | Mandated
CW | 405714 | Master Bridge Project | Bridge conditions, asset |  | 7559568 | 192200 | 368306 | 436995 | 554460 | 997890 | 1892360 | 4250011 | 0 | 12001779 | GT | Sam Updike, 533-9400
|  | Funds for capital repairs/replacement of small bridges and culverts as | protection |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | supdike@leegov.com
|  | identified throughout the year by inspections/critical events | Mandated
CW | 406024 | Roadway Beautification | Leescape Master Plan, |  | 7208197 | 149077 | 100000 | 100000 | 100000 | 100000 | 100000 | 500000 | 0 | 7857274 | AV | Bob DeBrock, 533-9425
|  | Funds for installation of landscaping on existing roads, including funds | RLAC priorities, com- |  | LS | LS | LS | LS | LS | LS | LS |  |  |  |  | bdebrock@leegov.com
|  | for grants to community groups ($100,000 per year) | munity interest
NM - Essential
CW | 406670 | Signal Upgrades/Equipment Replacement | Signal equipment con- |  | 633941 | 153575 | 350000 | 350000 | 350000 | 350000 | 350000 | 1750000 | 0 | 2537516 | GT | Mike Berens, 533-9500
|  | Fund to replace critical signal components as needed | dition, safety |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | mberens@leegov.com
Mandated
CW | 406713 | Master Signal Project/Major Intersections | Intersection conditions/ |  | 10753462 | 2242789 | 940000 | 650000 | 1300000 | 1300000 | 950000 | 5140000 | 0 | 18136251 | GT | Steve Jansen, 533-8503
|  | Funds for small-scale intersection improvements, including signalization | needs |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | sjansen@leegov.com
NM - Core Critical
CW | 406079 | ADA Plan Implementation | Federal Law, ADA plan |  | 0 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 1250000 | 0 | 1500000 | GT | Sarah Clarke, 533-8718
|  | Funds to make improvements on County roads per ADA Transition Plan | Mandated |  |  | CST | CST | CST | CST | CST | CST |  |  |  |  | sclarke@leegov.com
CW |  | Roadway Lighting Upgrade | Sustainability, operating |  | 0 | 0 | 0 | 450000 | 450000 | 450000 | 450000 | 1800000 | 0 | 1800000 | GT | Mike Say, 533-9514
|  | Funds to replace lighting fixtures with LED | cost reduction |  |  |  |  | CST | CST | CST | CST |  |  |  |  | msay@leegov.com
NM - Core Critical
CW |  | Work Order System | Age of current system, |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000 | 0 | 300000 | GT | Scott Palmer, 533-9500
|  | Update of Cartegraph work order system to handle work requests for DOT | opportunity for improved |  |  |  | CST | [8 empty] | spalmer@leegov.com
|  | Traffic and Engineering Services | efficiencies, accountability
NM - Essential
CW | 406763 | Sign Replacement Program | Sign conditions, safety, |  | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 250000 | 0 | 300000 | GT | Dan Vasiloff, 533-9500
|  | Funds to keep County-owned traffic regulatory and informational signage | liability |  |  | CST | CST | CST | CST | CST | CST |  |  |  |  | dvasiloff@leegov.com
|  | up to standards | Mandated
1,2 |  | Cape Coral Toll Facilities Painting | Current conditions, asset |  | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 750000 | 0 | 750000 | CAPE/MP | Sue Hopwood, 533-0157
|  | Funds to repaint the Cape Coral Bridge and related toll facilities | protection |  |  |  |  | CST | [6 empty] | SURP. | shopwood@leegov.com
|  |  | Mandated | [11 empty] | TOLLS
1,2 |  | Midpoint/LeeWay Facilities Painting | Current conditions, asset |  | 0 | 0 | 0 | 0 | 950000 | 0 | 0 | 950000 | 0 | 950000 | SURP. | Sue Hopwood, 533-0157
|  | Funds to repaint the Midpoint Bridge and related toll facilities, and the | protection | [5 empty] | CST | [5 empty] | TOLLS | shopwood@leegov.com
|  | LeeWay Service Center | Mandated
3 |  | Replace Overhead Sign Structures - Sanibel | Current conditions, asset |  | 0 | 0 | 70000 | 750000 | 0 | 0 | 0 | 820000 | 0 | 820000 | SANIBEL | Sue Hopwood, 533-0157
|  | Funds to replace signs structures on WB approach to Sanibel Bridge | protection, driver needs |  |  |  | DES | CST | [6 empty] | SURP. | shopwood@leegov.com
|  |  | Mandated | [11 empty] | TOLLS
CW |  | Overhead Sign Structures Evaluation | Maintenance obligations, |  | 0 | 0 | 130000 | 130000 | 130000 | 130000 | 130000 | 650000 | 0 | 650000 | GT | Mike Say, 533-9514
|  | Funds to inspect 1/5 of overhead sign structures every year | liability, FDOT standards |  |  |  | CST | CST | CST | CST | CST |  |  |  |  | msay@leegov.com
Mandated
5 |  | DOT Traffic Building Remodel | Operational inefficiencies, |  | 0 | 0 | 0 | 30000 | 450000 | 0 | 0 | 480000 | 0 | 480000 | AV | Mike Berens, 533-9500
|  | Funds to remodel building to shift personnel groups for more efficient operation | need for space |  |  |  |  | DES | CST | [6 empty] | mberens@leegov.com
NM - Core Critical
5 |  | Roundabout Landscaping | Safety/visibility, com- |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000 | AV | Bob DeBrock, 533-9425
|  | Funds to landscape Beth Stacy/Business Way and Sunshine/23rd roundabouts | munity beautification |  |  |  | LS | [8 empty] | bdebrock@leegov.com
NM - Essential
5 |  | Del Prado Blvd. Landscaping | Community beautification |  | 0 | 0 | 0 | 330000 | 0 | 0 | 0 | 330000 | 0 | 330000 | AV | Bob DeBrock, 533-9425
|  | Funds to install landscaping from Hancock Bridge Pkwy. to SR 78 | NM - Essential |  |  |  |  | LS | [7 empty] | bdebrock@leegov.com
|  | SUBTOTALS |  |  | 79889419 | 9512809 | 7608306 | 9276995 | 9584460 | 8627890 | 9172360 | 44270011 | 0 | 133672239
|  | TOTAL |  |  | 143579191 | 65227962 | 39209670 | 28678741 | 45369214 | 32244890 | 36428228 | 181930743 | 320021000 | 711036857
| NOTE: | Budget figures represent estimates for programming purposes. All dollar figures are subject to adjustment. Program year represents when funds are available, not necessarily when phase started or completed.
Totals exclude loan repayments/interest.
KEY (PHASES): |  | PRELIM = Preliminary Study; PD&E = Project Development & Environmental Study; DES = Design; ROW = Right-of-Way Acquisition; CST = Construction; CEI = Construction Engineering Inspection; PM = Project Management; LS = Landscaping;
MIT = Mitigation
KEY (FUNDS): |  | IF23 = Road Impact Fees from District 23; GT = Local Option Gas Taxes; CITY = City funds; PS = Public Safety funds; FDOT = Florida Dept. of Transportation; AV = Ad Valorem