## Sheet1
SUMMARY OF MAJOR ROAD PROJECTS PROGRAMMED BY LEE COUNTY - FY 16/17 TO FY 20/21
FY 98-15
COMM | PROJ. |  |  | LENGTH | PRIOR | FY 15/16 | [5 empty] | 5-YEAR |  | PROJECT | REVENUE | PROJECT
DIST. | # | PROJECT NAME | DRIVER | (MILES) | EXP. | BUDGET | 16/17 | 17/18 | 18/19 | 19/20 | 20/21 | TOTAL | 6-10 | TOTAL | SOURCE | MANAGER
MAJOR PROJECTS
2 | 205075 | Alico Rd 4L/Ben Hill-Airport Haul Rd (DESIGN UNDERWAY) | Added capacity for | 1.78 | 1553875 | 1031286 | 14800000 | 0 | 540000 | 0 | 0 | 15340000 | 0 | 17925161 | GT/IF25/ | Vince Miller, 5338577
|  | 4L widening, including on-road bike lanes and 12' multi-use paths | future RED developments |  | PRELIM/DES | DES/MIT | CST/CEI |  | LS | [5 empty] | AV/G | sclarke@leegov.com
|  | on both sides | NM - Discretionary/
Deferrable
Received $1 mill in funds from Economic DevelopmentTrust Fund
Construction moved to FY 16/17
2,5 | 209245 | Alico Rd. Connector/Alico Rd. to SR 82 opposite Sunshine Blvd. | People-to-jobs link, | 9 | 0 | 0 | 0 | 0 | 0 | 2240868 | 0 | 2240868 | 64000000 | 66240868 | IF25 | Vince Miller, 533-8577
|  | Funds to purchase ROW through Florida Rock property prior to 12/31/2020 per | Daniels Pkwy. relief | [6 empty] | ROW |  |  | ALL |  |  | vmiller@leegov.com
|  | purchase option agreement | NM - Core Critical
All | 206002 | Bicycle/Pedestrian Facilities | Implementation of bike- |  |  | 394000 | 3443861 | 2595910 | 1993259 | 1149680 | 1387945 | 10570655 | 2727076 | 13297731 | IF/GT | Lee Werst 533-8591
|  | Annual project for facilities on existing County-maintained roads | ped plan, BPAC prior- | [12 empty] | LCWerst@leegov.com
ities, Complete Streets
|  | Specific Projects: | principals
1 |  | Gulf Blvd. Path Widening, Wheeler Rd-1st St. W. | NM - Core Critical |  |  | 24000 | 108218 |  |  |  |  | 108218 |  | 132218 | IF21
[6 empty] | DES/SUR | CST/CEI
2 |  | Winkler Rd. Sidewalk/East Side, College Pkwy. to McGregor Blvd. |  |  |  | 97000 | 517000 |  |  |  |  | 517000 |  | 614000 | GT
[6 empty] | DES/SUR | CST/CEI
4 |  | Hancock Bridge Pkwy. Sidewalk/North Side, Moody Rd. to US 41 |  |  |  | 76000 | 948082 |  |  |  |  | 948082 |  | 1024082 | GT
[6 empty] | DES/SUR | CST/CEI
4 |  | Mariana Ave. Sidewalk/South Side, US 41 to Bus. 41 |  |  |  | 197000 | 1414216 |  |  |  |  | 1414216 |  | 1611216 | IF22
[6 empty] | DES/SUR | CST/CEI
1 |  | Veterans Pkwy.SW 10th St. to Skyline Blvd. | [7 empty] | 32950 | 189460 | 222410 |  | 222410 | IF22
[10 empty] | DSE/SUR | CST/CEI
1 |  | Veterans Pkwy.SW 3rd Pl to SW 2nd Ave | [7 empty] | 36914 | 212256 | 249170 |  | 249170 | IF22
[10 empty] | DES/SUR | CST/CEI
4 |  | Hancock Bridge Pkwy. Sidewalk/North Side, NE 16th Pl. to SE 24th Ave. |  |  |  |  | 233525 | 1354442 |  |  |  | 1587967 |  | 1587967 | GT
[7 empty] | DES/SUR | CST/CEI
2 |  | Boy Scout Dr. Pedestrian Safety Improvements, Summerlin Rd. to US 41 |  |  |  |  | 41011 | 237849 |  |  |  | 278860 |  | 278860 | GT
[7 empty] | DES/SUR | CST/CEI
1 |  | Stringfellow Rd SUP East, Sanibel Blvd to York Rd. | [5 empty] | 133027 | 771554 |  |  | 904581 |  | 904581 | GT
[8 empty] | DES/SUR | CST/CEI
4 |  | Hart Rd. SUP West, SR 78 to Forest Park Dr. | [5 empty] | 90623 | 525612 |  |  | 616235 |  | 616235 | GT
[8 empty] | DES/SUR | CST/CEI
2 |  | Beacon Manor Dr. Sidewalk, US 41 to S. Danley Dr. |  |  |  |  | 52378 |  | 303793 |  |  | 356171 |  | 356171 | IF23
[7 empty] | DES/SUR |  | CST/CEI
5 |  | E. 12th St. Sidewalk/North Side, Gerald Ave. to Joel Blvd. |  |  |  |  | 5416 | 31411 |  |  |  | 36827 |  | 36827 | IF23
[7 empty] | DES/SUR | CST/CEI
5 |  | Orange River Blvd. Palm Beach Blvd. to Lorraine Dr. | [8 empty] | 162946 | 162946 | 945085 | 1108031 | IF23
[11 empty] | DES/SUR |  | CST/CEI
5 |  | Tice St. Sidewalk/South Side, Lynneda Ave. to Ortiz Ave. | [6 empty] | 68529 | 397468 |  | 465997 |  | 465997 | IF23
[9 empty] | DES/SUR | CST/CEI
5 |  | Tice St. Sidewalk/South Side, Ortiz Ave. to Lexington Ave. | [6 empty] | 110848 | 642921 |  | 753769 |  | 753769 | IF23
[9 empty] | DES/SUR | CST/CEI
2 |  | Austin St. Woodland Ave to N. of Brantley | [5 empty] | 29268 | 169756 |  |  | 199024 |  | 199024 | IF23
[8 empty] | DES/SUR | CST/CEI
5 |  | Bell Blvd. SR 82 to Joel Blvd | [8 empty] | 268250 | 268250 | 1341250 | 1609500 | IF23
[11 empty] | DES/SUR |  | CST/CEI
3 |  | Estero Pkwy. |  |  |  |  | 124015 | 719290 |  |  |  | 843305 |  | 843305 | IF24, GT
|  | Represents 50% from County, other 50% from Village of Estero |  |  |  |  | DES/SUR | CST/CEI
2 |  | Alico Rd. Sidewalk/North Side, RR Crossing to Quaker Ln. | [6 empty] | 43167 |  | 250367 | 293534 |  | 293534 | IF24
[9 empty] | DES/SUR |  | CST/CEI
4 |  | Pine Rd. Allaire Ln to US 41 | [8 empty] | 75990 | 75990 | 440741 | 516731 | IF24
[11 empty] | DES/SUR |  | CST/CEI
3 |  | Bonita Beach Road I-75 to Bonita Grande | [7 empty] | 39427 | 228676 | 268103 |  | 268103 | IF25
[10 empty] | DES/SUR | CST/CEI
3 | 205724 | Big Carlos Pass Bridge | Bridge life cycle/con- |  |  | 8500000 |  | 3500000 |  |  | 40127057 | 43627057 |  | 52127057 | SANIBEL | Scott Gammon 533-8530
|  | Funds to replace 2L bascule bridge, fixed-span bridge an option | dition |  |  | PD&E/CST |  | DES |  |  | CST |  |  |  | SURP. | sgammon@leegov.com
|  |  | Mandated | [11 empty] | TOLLS
1,4 | 204088 | Burnt Store Road 4L (DES/ROW UNDERWAY) | Future growth, safety, | 4.3 | 11014716 | 24433658 | 5900000 | 897754 | 10450000 |  | 630000 | 17877754 | 0 | 53326128 | CAPE/MP | Vince Miller, 533-8577
|  | SR 78 (Pine Island Road) to Van Buren Parkway (IN SEGMENTS) | City priority and shared |  | DES/ROW/CST | DES/ROW/ | CST/CEI | CST/CEI | CST/CEI |  | LS |  |  |  | SURP. | vmiller@leegov.com
|  | - including on-road bike lanes, 10' multi-use path on east side, 6' side | funding via surplus tolls |  |  | CST/CEI | Central Seg. | LS | South Seg. | [5 empty] | TOLLS/
|  | walk on west side | NM - Essential |  |  | North Seg. | [8 empty] | IF22/TRIP/
|  | PER BOCC ACTION 11/19/13, CONSTRUCTION STARTING WITH NORTH | [12 empty] | GIF
SEGMENT (DIPLOMAT PKWY. TO VAN BUREN PKWY.)
1,2 | 209248 | Cape Coral Bridge WB Span Replacement | Age/condition, escalating |  | 0 | 0 | 0 | 0 | 1425968 | 1000000 | 4000000 | 6425968 | 83925968 | 90351936 | CAPE/MP | Scott Gammon 533-8530
|  | Accumulation of Cape and Midpoint surplus toll funds toward replacement of | maintenance costs | [5 empty] | DES | DES | DES |  |  |  | SURP. | sgammon@leegov.com
|  | westbound span of Cape Coral Bridge by approximately 2028 | Mandated | [11 empty] | TOLLS
2 | 209249 | Colonial Blvd. Alternatives Analysis | LOS F per Concurrency |  | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 350000 | 0 | 350000 | IF23 | TBD
|  | Funds to evaluate improvement options between McGregor Blvd. and US 41 | report | [5 empty] | Study
NM - Essential
4 | 205082 | Corbett Rd. Widening/Resurfacing | Substandard condition, |  | 23426 | 816574 | 185000 | 0 | 0 | 0 | 0 | 185000 | 0 | 1025000 | GT | Vince Miller, 533-8577
|  | Diplomat Pkwy. to Littleton Rd - Widen pavement for 11-ft lanes, including | Federal facilities in City |  | DES | DES/CST | CST | [8 empty] | Vmiller@leegov.com
|  | 8-ft off-road path on west side | NM - Essential
Additional funds for CST needed, CST in 16/17
3 | 205067 | Estero Blvd. Improvements (SEGMENT 1 DES UNDERWAY, CST THIS YEAR) | Town request, reflective | 6 | 3320567 | 15461313 | 3564000 | 8350000 | 300000 | 8475000 | 0 | 20689000 | 19540000 | 59010880 | GT/IF24/ | Rob Phelan, 533-8594
|  | Phased reconstruction of County roadway within Town, including adding | of Town's Streetscape |  | PRELIM/DES | DES/CST/CEI | DES | CST/CEI | LS | CST/CEI |  |  | CST/CEI |  | GIF | rphelan@leegov.com
|  | trolley stops, bike lanes and sidewalks on both sides, and replacement | Master Plan, Complete |  | CST
|  | of City water lines and County sewer lines (costs don't reflect utility | Streets principals |  |  | Segment 1 CST | Segment 3-6 | Segment 3 | Segment 1 | Segment 4 |  |  | Segments 5
|  | replacements). | NM - Essential |  |  | Segment 2 DES/ | DES | CST | LS | CST |  |  | and 6
|  | PER BOCC ACTION 11/19/13, CONSTRUCTION WILL MOVE IN |  |  |  | CST
CONSECUTIVE SEGMENTS FROM NORTH TO SOUTH STARTING AT
CRESCENT ST., WITH CST FUNDING EVERY OTHER YEAR.
IMPROVEMENT AT FOOT OF MATANZAS PASS BRIDGE NOT YET
IDENTIFIED AND FUNDED, TO BE EVALUATED IN FDOT PD&E STUDY.
5 | 209246 | Gunnery Rd./8th St. Intersection Improvements | Intersection control |  | 200000 | 60000 | 1274819 | 0 | 0 | 0 | 0 | 1274819 | 0 | 1534819 | GT | Vince Miller, 533-8577
|  | Signalization and turn lane improvements | needed |  | DES | ROW | CST | [7 empty] | FDOT | vmiller@leegov.com
NM- Core Critical
5 | 205063 | Homestead 4L/Sunrise-Alabama | LOS, community interest | 2.25 | 2481844 | 17877432 | 0 | 690000 | 0 | 0 | 0 | 690000 | 0 | 21049276 | IF23/GT/ | Vince Miller, 533-8577
|  | 4L widening, south of Sunrise Blvd. to Alabama Rd., including on-road | Mandated |  | DES/ROW | DES/ROW/ |  | LS | [6 empty] | GIF | vmiller@leegov.com
|  | bike lanes and sidewalks on both sides |  |  |  | CST
| 205083 | Hickory Bridge Replacements | Age/condition, escalting |  | 0 | 0 | 0 | 3798864 | 0 | 0 | 0 | 3798864 | 33791687 | 37590551 | SANIBEL | Scott Gammon 533-8530
|  | Project combines New Pass, Little Carlos and Big Hickory bridges into one project | maintenance costs |  |  |  |  | DES | [6 empty] | SURP. TOLLS/GT/GIF | sgammon@leegov.com
GIF
4 | 200611 | Kismet/Littleton Realignment | System continuity, City |  | 0 | 500000 | 1610000 | 2030000 | 0 | 0 | 0 | 3640000 | 0 | 4140000 | IF22 | Vince Miller, 533-8577
|  | Realignment of eastern end of Kismet Pkwy. to connect directly to | request, fund-sharing |  |  | DES | ROW | CST | [6 empty] | CITY | vmiller@leegov.com
|  | Littleton Rd., including on-road bike lanes and sidewalks on both sides | interlocal (if executed)
|  | (amounts reflect total project cost | NM - Essential
3 | 205028 | Littleton Road | Congested |  | 0 | 0 | 0 | 0 | 0 | 0 | 2900000 | 2900000 | 12100000 | 15000000 | GT | Vince Miller, 533-8577
|  | Widen existing 2 lane rural road to 4 lanes, including on road bike lanes and sidewalks | Expected to worsen with | [7 empty] | DES/ROW |  | CST/CEI |  |  | vmiller@leegov.com
Kismet/Littleton
Realignment
2,4 | 240613 | Ortiz 4L/Colonial-MLK | Parallel reliever to I-75, | 1.73 | 0 | 0 | 0 | 2250000 | 0 | 12450000 | 0 | 14700000 | 519000 | 15219000 | IF23 | Rob Phelan, 533-8594
|  | 4L widening, Colonial Blvd. to SR 82 (Dr. Martin Luther King, Jr. Blvd.), | access to jail and EMS, |  |  |  |  | DES |  | CST |  |  | LS |  | GIF/GT | rphelan@leegov.com
|  | including on-road bike lanes and sidewalks on both sides | projected LOS | [11 empty] | BP
2 | 205081 | Palomino Lane Improvements | Improved traffic flow, bike- | 1.5 | 0 | 212978 | 1850000 | 0 | 0 | 0 | 0 | 1850000 | 0 | 2062978 | IF/GT | Vince Miller, 533-8577
|  | Addition of 8-foot off-road path on one side and left turn lanes at certain | ped safety, community |  |  | DES | CST | [8 empty] | vmiller@leegov.com
|  | key locations, Daniels Pkwy. to Penzance Blvd. Future road impact fees | request
|  | provided by City per annexation interlocal to be earmarked for project. | NM - Essential
ALL | 206759 | Signal System ATMS Upgrade | Maximizes efficient use |  | 2939162 | 834880 | 750000 | 750000 | 750000 | 750000 | 750000 | 3750000 | 0 | 7524042 | GT | Rob Price, 533-9500
|  | Upgrade signal system and TOC equipment, install ITS field equipment to | of existing capacity |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | rprice@leegov.com
|  | support ATMS operations on County roads | NM - Core Critical
5 | 200614 | Sunshine Blvd./8th St. W. Roundabout | Intersection control |  | 0 | 0 | 0 | 200000 | 260000 | 0 | 700000 | 1160000 | 0 | 1160000 | GT | Vince Miller, 533-8577
|  |  | NM- Core Critical |  |  |  |  | DES | ROW |  | CST |  |  |  |  | vmiller@leegov.com
2 | 204053 | Three Oaks Parkway Extension North | Extends major arterial, | 3.5 | 6927129 | 5592428 | 9800000 | 7000000 | 0 | 31400000 | 0 | 48200000 | 1050000 | 61769557 | IF23,24 | Vince Miller, 533-8577
|  | New 4L, N. of Alico Rd. to Daniels Pkwy., including on-road bike lanes | parallel reliever to I-75 |  | DES/ROW | DES/ROW | DES/ROW | ROW |  | CST/CEI |  |  | LS |  | GIF/GT | vmiller@leegov.com
|  | and sidewalks on both sides | NM - Essential
1,2,3 | 205818 | Toll Interoperability | Age of equipment, rapid |  | 0 | 300000 | 150000 | 150000 | 150000 | 150000 | 150000 | 750000 | 0 | 1050000 | SURP. | Sue Hopwood, 533-0157
|  | Funds for hardware/software changes to maintain interoperability with other toll | technology changes |  |  | CST | CST | CST | CST | CST | CST |  |  |  | TOLLS | shopwood@leegov.com
|  | agencies | NM - Core Critical
1,2,3 | 200615 | Toll System Replacement | Age of equipment, rapid |  | 0 | 0 | 3250000 | 3250000 | 0 | 0 | 0 | 6500000 | 0 | 6500000 | SURP. | Sue Hopwood, 533-0157
|  | Funds for complete replacement due to technology changes | technology changes |  |  |  | CST | CST | [6 empty] | TOLLS | shopwood@leegov.com
NM - Core Critical
|  | SUBTOTALS |  |  | 28460719 | 76408549 | 46577680 | 35462528 | 16219227 | 57615548 | 50645002 | 206519985 | 220380807 | 541946715
MAJOR MAINTENANCE PROJECTS
CW | 404683 | Road Resurface/Rebuild Program | Pavement rating system, |  | 57996798 | 7157374 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 20000000 | 0 | 85154172 | GT | Dirk Danley, 533-9300
|  | Funds for rebuilding/resurfacing County-maintained roads as identified | complaints, asset prot. |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | ddanley@leegov.com
|  | under systematic evaluation | Mandated
5 | 406715 | Road Resurface/Rebuild Program - Lehigh Acres |  |  | 0 | 0 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 25000000 | 0 | 25000000 | GIF | Dirk Danley, 533-9300
|  | Funds for rebuilding/resurfacing roads in Lehigh Acres |  |  |  |  | CST | CST | CST | CST | CST |  |  |  |  | ddanley@leegov.com
CW | 405714 | Master Bridge Project | Bridge conditions, asset |  | 7748068 | 370506 | 436995 | 554460 | 997890 | 1892360 | 250000 | 4131705 | 0 | 12250279 | GT | Ehab Guiguis, 533-9400
|  | Funds for capital repairs/replacement of small bridges and culverts as | protection |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | eguirguis@leegov.com
|  | identified throughout the year by inspections/critical events | Mandated
CW | 406024 | Roadway Beautification | Leescape Master Plan, |  | 7325175 | 132098 | 100000 | 100000 | 100000 | 100000 | 100000 | 500000 | 0 | 7957273 | GIF | Bob DeBrock, 533-9425
|  | Funds for installation of landscaping on existing roads, including funds | RLAC priorities, com- |  | LS | LS | LS | LS | LS | LS | LS |  |  |  |  | bdebrock@leegov.com
|  | for grants to community groups ($100,000 per year) | munity interest
NM - Essential
CW | 406670 | Signal Upgrades/Equipment Replacement | Signal equipment con- |  | 748139 | 350362 | 350000 | 350000 | 350000 | 350000 | 350000 | 1750000 | 0 | 2848501 | GT | Mike Berens, 533-9500
|  | Fund to replace critical signal components as needed | dition, safety |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | mberens@leegov.com
Mandated
CW | 406713 | Master Signal Project/Major Intersections | Intersection conditions/ |  | 11421919 | 2457496 | 1500000 | 650000 | 1300000 | 1200000 | 950000 | 5600000 | 0 | 19479415 | GT | Scott Gammon 533-8530
|  | Funds for small-scale intersection improvements, including signalization | needs |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | sgammon@leegov.com
NM - Core Critical
CW | 406079 | ADA Plan Implementation | Federal Law, ADA plan |  | 0 | 482408 | 250000 | 250000 | 250000 | 250000 | 250000 | 1250000 | 0 | 1732408 | GT | Dave Murphy 533-8578
|  | Funds to make improvements on County roads per ADA Transition Plan | Mandated |  |  | CST | CST | CST | CST | CST | CST |  |  |  |  | dmurphy@leegov.com
CW |  | Roadway Lighting Upgrade | Sustainability, operating |  | 0 | 0 | 450000 | 450000 | 450000 | 450000 | 450000 | 2250000 | 0 | 2250000 | GT | Mike Padgett 533-9500
| 406080 | Funds to replace lighting fixtures with LED | cost reduction |  |  |  |  | CST | CST | CST | CST |  |  |  |  | mpadgett@leegov.com
NM - Core Critical
CW | 406714 | Signal Network | Age of current system, |  | 0 | 0 | 120000 | 120000 | 120000 | 120000 | 120000 | 600000 | 0 | 600000 | GT | Rob Radford, 5330110
|  | Upgrade existing Traffic Signal Network | disaster recover/backup |  |  |  | CST | [8 empty] | rradford@leegov.com
|  | Traffic and Engineering Services | security
NM - Essential
CW | 406763 | Sign Replacement Program/Raised Pavement Markers | Sign conditions, safety, |  | 50000 | 50000 | 150000 | 150000 | 150000 | 150000 | 150000 | 750000 | 0 | 850000 | GT | Dan Vasiloff, 533-9500
|  | Funds to keep County-owned traffic regulatory and informational signage | liability |  |  | CST | CST | CST | CST | CST | CST |  |  |  |  | dvasiloff@leegov.com
|  | up to standards | Mandated
1,2 | 406760 | Cape Coral Toll Facilities Painting | Current conditions, asset |  | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 750000 | 0 | 750000 | CAPE/MP | Sue Hopwood, 533-0157
|  | Funds to repaint the Cape Coral Bridge and related toll facilities | protection |  |  |  | CST | [7 empty] | SURP. | shopwood@leegov.com
|  |  | Mandated | [11 empty] | TOLLS
1,2 | 406761 | Midpoint/LeeWay Facilities Painting | Current conditions, asset |  | 0 | 0 | 0 | 950000 | 0 | 0 | 0 | 950000 | 0 | 950000 | SURP. | Sue Hopwood, 533-0157
|  | Funds to repaint the Midpoint Bridge and related toll facilities, and the | protection |  |  |  |  | CST | [6 empty] | TOLLS | shopwood@leegov.com
|  | LeeWay Service Center | Mandated
3 | 406762 | Replace Overhead Sign Structures - Sanibel | Current conditions, asset |  | 0 | 70000 | 750000 | 0 | 0 | 0 | 0 | 750000 | 0 | 820000 | SANIBEL | Sue Hopwood, 533-0157
|  | Funds to replace signs structures on WB approach to Sanibel Bridge | protection, driver needs |  |  | DES | CST | [7 empty] | SURP. | shopwood@leegov.com
|  |  | Mandated | [11 empty] | TOLLS
CW | 408944 | Overhead Sign Structures Evaluation | Maintenance obligations, |  | 0 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 650000 | 0 | 780000 | GT | Mike Padgett 533-9500
|  | Funds to inspect 1/5 of overhead sign structures every year | liability, FDOT standards |  |  |  | CST | CST | CST | CST | CST |  |  |  |  | Mpadgett@leegov.com
Mandated
5 | 448920 | Del Prado Blvd. Landscaping | Community beautification |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000 | 0 | 300000 | GIF | Bob DeBrock, 533-9425
|  | Funds to install landscaping from Hancock Bridge Pkwy. to SR 78 | NM - Essential |  |  |  | LS | [8 empty] | bdebrock@leegov.com
|  | SUBTOTALS |  |  | 85290099 | 11200244 | 14286995 | 12704460 | 12847890 | 13642360 | 11750000 | 65231705 | 0 | 161722048
|  | TOTAL |  |  | 113750818 | 87608793 | 60864675 | 48166988 | 29067117 | 71257908 | 62395002 | 271751690 | 220380807 | 703668763
| NOTE: | Budget figures represent estimates for programming purposes. All dollar figures are subject to adjustment. Program year represents when funds are available, not necessarily when phase started or completed.
Totals exclude loan repayments/interest.
KEY (PHASES): |  | PRELIM = Preliminary Study; PD&E = Project Development & Environmental Study; DES = Design; ROW = Right-of-Way Acquisition; CST = Construction; CEI = Construction Engineering Inspection; PM = Project Management; LS = Landscaping;
MIT = Mitigation
KEY (FUNDS): |  | IF23 = Road Impact Fees from District 23; GT = Local Option Gas Taxes; CITY = City funds; PS = Public Safety funds; FDOT = Florida Dept. of Transportation; AV = Ad Valorem; GIF = Growth Increment Funding