## Sheet1
DRAFT SUMMARY OF MAJOR ROAD PROJECTS PROGRAMMED BY LEE COUNTY - FY 19/20 TO FY 23/24
2019-10-18
FY 98-18
COMM | PROJ. |  |  | LENGTH | PRIOR | 18/19 | [5 empty] | 5-YEAR |  | PROJECT | REVENUE | PROJECT
DIST. | # | PROJECT NAME | DRIVER | (MILES) | EXP. | BUDGET | 19/20 | 20/21 | 21/22 | 22/23 | 23/24 | TOTAL | 6-10 | TOTAL | SOURCE | MANAGER
MAJOR PROJECTS
2 | 205075 | Alico Rd 4L/Ben Hill-Airport Haul Rd (DESIGN UNDERWAY) | Added capacity for | 1.78 | 3936167 | 18690391 | 540000 | 0 | 0 | 0 | 0 | 540000 | 0 | 23166558 | GT/IF25/ | Vince Miller 533-8577
|  | 4L widening, including on-road bike lanes and 12' multi-use paths | future RED developments |  | PRELIM/DES | DES/MIT | LS | [7 empty] | AV/G | vmiller@leegov.com
|  | on both sides | NM - Discretionary/ |  |  | CST
Deferrable
Received $1 mill in funds from Economic DevelopmentTrust Fund
Construction moved to FY 16/17
2,5 | 209245 | Alico Rd. Connector/Alico Rd. to SR 82 opposite Sunshine Blvd. | People-to-jobs link, | 9 | 3936886 | 0 | 7240686 | 0 | 0 | 0 | 0 | 7240686 | 96881486 | 108059058 | IF25 | Vince Miller, 533-8577
|  | Funds to purchase ROW through Florida Rock property prior to 12/31/2020 per | Daniels Pkwy. relief |  |  |  | ROW | 0 |  |  |  |  | ALL |  | GT | vmiller@leegov.com
|  | purchase option agreement | NM - Core Critical |  |  |  | PD&E
All | 206002 | Bicycle/Pedestrian Facilities | Implementation of bike- |  | 18840810 | 7077912 | 728710 | 962080 | 5208768 | 0 | 7149367 | 14048925 | 8975012 | 48942659 | IF/GT | TBD
|  | Annual project for facilities on existing County-maintained roads | ped plan, BPAC prior-
ities, Complete Streets
|  | Specific Projects: | principals
1 |  | Veterans Pkwy.SW 10th St. to Skyline Blvd. | 2016 Priority #22 |  |  |  | 40500 | 0 | 232850 | 0 | 0 | 273350 |  | 273350 | IF22
[7 empty] | DES/SUR |  | CST/CEI
1 |  | Veterans Pkwy.SW 3rd Pl to SW 2nd Ave | 2016 Priority #23 |  |  |  | 44910 | 0 | 258225 | 0 | 0 | 303135 |  | 303135 | IF22
[7 empty] | DES/SUR |  | CST/CEI
|  | Hancock Bridge Pkwy US 41 to Moody River | 2013 Priority #6 |  |  |  | 600000 | 0 | 0 | 0 | 0 | 600000 |  | 600000 | GT
CST/CEI
adding funds in 19/20 for construction
4 |  | Hancock Bridge Pkwy. Orange Grove - 4055 Hancock | 2017 Priority #4 |  |  |  | 0 | 0 | 363007 | 0 | 696791 | 1059798 |  | 1059798 | IF22
[9 empty] | DES/UR |  | CST/CEI
4 |  | Hancock Bridge Pkwy. Sidewalk/North Side, NE 16th Pl. to SE 24th Ave. | 2013 Priority #8 | [10 empty] | 0 | GT
2 |  | Beacon Manor Dr. Sidewalk, US 41 to S. Danley Dr. | 2014 Priority #1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IF23
[6 empty] | DES/SUR | CST/CEI
5 |  | Orange River Blvd. Palm Beach Blvd. to Lorraine Dr. | 2016 Priority #4 |  |  |  | 0 | 0 | 2393870 | 0 | 0 | 2393870 | 8226729 | 10620599 | IF23
[9 empty] | DES/SUR/ ROW | [5 empty] | GT
5 |  | Tice St. Sidewalk/South Side, Lynneda Ave. to Ortiz Ave. | 2015 Priority #2 |  |  |  | 0 | 90000 | 517000 |  | 0 | 607000 |  | 607000 | IF23
[8 empty] | DES/SUR | CST/CEI
5 |  | Tice St. Sidewalk/South Side, Ortiz Ave. to Lexington Ave. | 2015 Priority #5 |  |  |  | 0 | 0 | 154816 | 0 | 891000 | 1045816 |  | 1045816 | IF23
[9 empty] | DES/SUR |  | CST/CEI
5 |  | Bell Blvd. SR 82 to Sunrise | 2016 Priority #3 |  |  |  | 0 | 623080 |  | 0 | 3582670 | 4205750 |  | 4205750 | GT
[8 empty] | DES/SUR |  |  | CST/CEI
|  | Westgate N Lee-Sunshine | 2017 Priority #2 |  |  |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | IF23
[10 empty] | DES/SUR |  |  | CST/CEI
|  | Westgate S Lee-Sunshine | 2017 Priority #3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | IF23
[10 empty] | DES/SUR |  |  | CST/CEI
2 |  | Alico Rd. Sidewalk/North Side, RR Crossing to Quaker Ln. | 2015 Priority #27 |  |  |  | 0 | 0 | 1289000 | 0 | 1848769 | 3137769 |  | 3137769 | IF24
[9 empty] | DES/SUR/ ROW |  | CST/CEI
4 |  | Pine Rd. Allaire Ln to US 41 | 2016 Priority #28 |  |  |  | 0 | 0 | 0 | 0 | 130137 | 130137 | 748283 | 878420 | IF24
DES/SUR
|  | Pine Ridge Rd. Stevens-Summerlin | 2017 Priority #12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IF24
3 |  | Bonita Beach Road I-75 to Bonita Grande | 2016 Priority #8 |  |  |  | 43300 | 249000 | 0 | 0 | 0 | 292300 |  | 292300 | IF25
[7 empty] | DES/SUR | CST/CEI
3 | 205724 | Big Carlos Pass Bridge | Bridge life cycle/con- |  | 1106865 | 7393135 | 0 | 0 | 47810820 |  | 0 | 47810820 |  | 56310820 | SANIBEL | Tom Marquardt
|  | Funds to replace 2L bascule bridge, fixed-span bridge an option | dition |  | PD&E | PD&E/DES |  |  | CST/CEI | [5 empty] | SURP. | tmarquardt@leegov.com
|  |  | Mandated | [11 empty] | TOLLS
1,4 | 204088 | Burnt Store Road 4L (DES/ROW UNDERWAY) | Future growth, safety, | 4.3 | 34208307 | 20596625 | 18000000 | 0 | 0 | 0 | 0 | 18000000 | 0 | 72804932 | CAPE/MP | Vince Miller, 533-8577
|  | SR 78 (Pine Island Road) to Van Buren Parkway (IN SEGMENTS) | City priority and shared |  | DES/ROW/CST | DES/ROW/ | CST/CEI | [7 empty] | SURP. | vmiller@leegov.com
|  | - including on-road bike lanes, 10' multi-use path on east side, 6' side | funding via surplus tolls |  |  | CST/CEI | LS | [7 empty] | TOLLS/
|  | walk on west side | NM - Essential |  |  | North Seg. | [8 empty] | IF22/TRIP/
|  | PER BOCC ACTION 11/19/13, CONSTRUCTION STARTING WITH NORTH |  |  |  | Central Seg | [8 empty] | GIF
SEGMENT (DIPLOMAT PKWY. TO VAN BUREN PKWY.)
1,2 | 209248 | Cape Coral Bridge WB Span Replacement | Age/condition, escalating |  | 0 | 0 | 0 | 0 | 9000000 | 0 | 0 | 9000000 | 99100000 | 108100000 | CAPE/MP | Tom Marquardt
|  | Accumulation of Cape and Midpoint surplus toll funds toward replacement of | maintenance costs | [5 empty] | DES | [5 empty] | SURP. | tmarquardt@leegov.com
|  | westbound span of Cape Coral Bridge by approximately 2028 | Mandated | [11 empty] | TOLLS
2 | 209249 | Colonial Blvd. Alternatives Analysis | LOS F per Concurrency |  | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | IF23 | Steve Jansen 533-8503
|  | Funds to evaluate improvement options between McGregor Blvd. and US 41 | report |  |  | Study | [9 empty] | sjansen@leegov.com
NM - Essential
0 | 200669 | Corkscrew Road | Reduce congestion |  | 1282970 | 5875272 | 1015000 | 23590772 |  | 17795308 | 0 | 42401080 | 0 | 49559322 | GF | Tom Marquardt 533-8530
|  | Ben Hill Griffin to Alico Road |  |  |  |  | ROW | CST/CEI |  | CST/CEI |  |  |  |  | Debt | tmarquardt@leegov.com
3 | 205067 | Estero Blvd. Improvements | Town request, reflective | 6 | 23489969 | 32483599 | 24700000 | 820000 | 0 | 0 | 0 | 25520000 |  | 81493568 | GT/IF24/ | Rob Phelan, 533-8594
|  | Phased reconstruction of County roadway within Town, including adding | of Town's Streetscape |  | PRELIM/DES | DES/CST/CEI | CST/CEI | LS | [6 empty] | GIF | rphelan@leegov.com
|  | trolley stops, bike lanes and sidewalks on both sides, and replacement | Master Plan, Complete |  | CST
|  | of City water lines and County sewer lines (costs don't reflect utility | Streets principals |  | Segment 1 CST | Segment 2-4 | Segments
|  | replacements). | NM - Essential |  |  | CST/CEI | 43591
CST/CEI
| NEW | Estero Blvd. at Crescent St. Signal | TPI Development |  |  | 60000 | 0 | 565000 | 0 | 0 | 0 | 0 | 0 | 625000 | GT | TBD
[6 empty] | DES/CST/CEI |  | CST/CEI | [6 empty] | Grant
4 | 200672 | Gateway at Commerce Lakes Roundabout | Improve safety without |  |  | 200000 | 1400000 | 0 | 0 | 0 | 0 | 1400000 |  | 1600000 | GT | Alex Slaibe 533-8141
|  |  | adding delay |  |  | DES | CEI/CST | [8 empty] | aslaibe@leegov.com
4 | 200672 | Gateway at Griffin Roundabout | Improve safety without |  |  | 200000 | 0 | 1400000 | 0 | 0 | 0 | 1400000 |  | 1600000 | GT | Alex Slaibe 533-8141
|  |  | adding delay |  |  | DES |  | CEI/CST | [7 empty] | aslaibe@leegov.com
5 | 209246 | Gunnery Rd./8th St. Intersection Improvements | Intersection control |  |  | 1579817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579817 | GT | Alex Slaibe
|  | Signalization and turn lane improvements | needed |  |  | DES/ROW | [8 empty] | FDOT | aslaibe@leegov.com
NM- Core Critical
5 | 205063 | Homestead 4L/Sunrise-Alabama | LOS, community interest | 2.25 | 13438332 | 9784294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23222626 | IF23/GT/ | Vince Miller, 533-8577
|  | 4L widening, south of Sunrise Blvd. to Alabama Rd., including on-road | Mandated |  | DES/ROW | DES/ROW/ | [8 empty] | GIF | vmiller@leegov.com
|  | bike lanes and sidewalks on both sides |  |  | CST, CEI | CST, CEI, LS
| 205083 | Hickory Bridge Replacements | Age/condition, escalting |  | 0 | 0 | 0 | 0 | 4266000 | 0 | 0 | 4266000 | 46716000 | 50982000 | SANIBEL | TBD
|  | Project combines New Pass, Little Carlos and Big Hickory bridges into one project | maintenance costs | [5 empty] | DES | [5 empty] | SURP. TOLLS/GT/GIF
GIF
5 | 200637 | Lee Boulevard/Lee Street Traffic Signal | Safety issue |  | 68896 | 481104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | GT | Steve Jansen 533-8503
[6 empty] | DES, CST | [9 empty] | sjansen@leegov.com
|  | Lee Boulevard/Joan Avenue Traffic Signal |  |  |  |  | 0 | 150000 | 400000 | 0 |  | 550000 | 0 | 550000
[8 empty] | DES | CST
3 | 205028 | Littleton Road | Congested |  | 88116 | 2371883 | 1000000 | 12000000 | 0 | 0 | 0 | 13000000 | 400000 | 15859999 | GT | Vince Miller, 533-8577
|  | Widen existing 2 lane rural road to 4 lanes, including on road bike lanes and sidewalks | Expected to worsen with |  | Study | DES/ROW | ROW | CST/CEI |  |  |  |  | LS |  |  | vmiller@leegov.com
Kismet/Littleton
Realignment
2,4 | 240613 | Ortiz 4L/Colonial-MLK | Parallel reliever to I-75, | 1.73 | 2912 | 2347088 | 0 | 0 | 20025000 |  | 519000 | 20544000 | 0 | 22894000 | IF23 | Rob Phelan, 533-8594
|  | 4L widening, Colonial Blvd. to SR 82 (Dr. Martin Luther King, Jr. Blvd.), | access to jail and EMS, |  |  | DES/MIT |  |  | CST/CEI |  | LS |  |  |  | GIF/GT | rphelan@leegov.com
|  | including on-road bike lanes and sidewalks on both sides | projected LOS | [11 empty] | BP
2 | 205081 | Ortiz 4L/MLK-Luckett/Luckett-I75 | Improved traffic flow, bike- | 1.25 | 9244179 | 561502 | 0 | 0 | 1450000 | 0 | 0 | 1450000 | 22044000 | 33299681 | IF/GT | Rob Phelan, 533-8594
|  | Widen existing 2-lane to 4-lane, including on-road bike lanes and sidewalks | ped safety, community |  | DES/ROW | ROW |  |  | DES | [6 empty] | rphelan@leegov.com
|  | on both sides | request
NM - Essential
ALL | 206759 | Signal System ATMS Upgrade | Maximizes efficient use |  | 4707142 | 1434190 | 750000 | 750000 | 750000 | 750000 | 750000 | 3750000 | 0 | 9891332 | GT | Rob Price, 533-9500
|  | Upgrade signal system and TOC equipment, install ITS field equipment to | of existing capacity |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | rprice@leegov.com
|  | support ATMS operations on County roads | NM - Core Critical
5 | 200614 | Sunshine Blvd./8th St. W. Roundabout | Intersection control |  | 0 | 550000 | 0 | 1440000 | 0 | 0 | 0 | 1440000 | 0 | 1990000 | GT | Alejandro Slaibe, 533-8141
|  |  | NM- Core Critical |  |  | DES, ROW |  | CST/CEI | [6 empty] | GIF | aslaibe@leegov.com
2 | 204053 | Three Oaks Parkway Extension North | Extends major arterial, | 3.5 | 7887051 | 22097224 | 20900000 | 20930000 | 0 | 31720000 | 0 | 73550000 | 1050000 | 104584275 | IF23,24 | Vince Miller, 533-8577
|  | New 4L, N. of Alico Rd. to Daniels Pkwy., including on-road bike lanes | parallel reliever to I-75 |  | DES/ROW | DES/ROW | ROW | CST/CEI | 0 | CST/CEI | 0 |  | LS |  | GIF/GT | vmiller@leegov.com
|  | and sidewalks on both sides | NM - Essential |  |  |  | CST/CEI
1,2,3 | 205818 | Toll Interoperability | Age of equipment, rapid |  | 151275 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 750000 | 0 | 1051275 | SURP. | Sue Hopwood, 533-0157
|  | Funds for hardware/software changes to maintain interoperability with other toll | technology changes |  |  | CST | CST | CST | CST | CST | CST |  |  |  | TOLLS | shopwood@leegov.com
|  | agencies | NM - Core Critical
1,2,3 | 200615 | Toll System Replacement | Age of equipment, rapid |  | 0 | 0 | 0 | 250000 | 0 | 13000000 | 0 | 13250000 | 0 | 13250000 | SURP. | Sue Hopwood, 533-0157
|  | Funds for complete replacement due to technology changes | technology changes |  |  |  |  | Study |  | CST |  |  |  |  | TOLLS | shopwood@leegov.com
NM - Core Critical
|  | SUBTOTALS |  |  | 122389877 | 134284036 | 76467987 | 63007852 | 89060588 | 63415308 | 8568367 | 300520102 | 284141510 | 855340859
MAJOR MAINTENANCE PROJECTS
CW | 404683 | Road Resurface/Rebuild Program | Pavement rating system, |  | 50957652 | 3621985 | 2900000 | 4000000 | 4000000 | 4000000 | 4000000 | 18900000 | 0 | 73479637 | GT | Dirk Danley, 533-9300
|  | Funds for rebuilding/resurfacing County-maintained roads as identified | complaints, asset prot. |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | ddanley@leegov.com
under systematic evaluation
5 | 406715 | Road Resurface/Rebuild Program - Lehigh Acres | Pavement rating system, |  | 3053925 | 7502586 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 25000000 | 0 | 25000000 | GIF | Dirk Danley, 533-9300
|  | Funds for rebuilding/resurfacing roads in Lehigh Acres | complaints, asset prot. |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | ddanley@leegov.com
| 400951 | Road Resurface/Rebuild Program - Del Prado | Paving rating system |  | 0 | 2300000 | 1150000 | 1150000 | 0 | 0 | 0 | 2300000 | 0 | 2300000 | GT | Dirk Danley, 533-9300
|  | From Veterans to Pine Island |  |  |  | CST | CST | CST | [7 empty] | ddanley@leegov.com
CW | 405714 | Master Bridge Project | Bridge conditions, asset |  | 8377399 | 1056853 | 1010000 | 775000 | 815000 | 825000 | 825000 | 4250000 | 0 | 13684252 | GT | Avelino Cancel, 533-9400
|  | Funds for capital repairs/replacement of small bridges and culverts as | protection |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | acancel@leegov.com
|  | identified throughout the year by inspections/critical events | Mandated
CW | 406024 | Roadway Beautification | Leescape Master Plan, |  | 4910200 | 195750 | 100000 | 100000 | 100000 | 100000 | 100000 | 500000 | 0 | 5605950 | GIF | Bob DeBrock, 533-9425
|  | Funds for installation of landscaping on existing roads, including funds | RLAC priorities, com- |  | LS | LS | LS | LS | LS | LS | LS |  |  |  |  | bdebrock@leegov.com
|  | for grants to community groups ($100,000 per year) | munity interest
NM - Essential
CW | 406670 | Signal Upgrades/Equipment Replacement | Signal equipment con- |  | 1258994 | 998096 | 350000 | 350000 | 350000 | 350000 | 350000 | 1750000 | 0 | 4007090 | GT | Mike Berens, 533-9500
|  | Fund to replace critical signal components as needed | dition, safety |  | DES,CST | CST | CST | CST | CST | CST | CST |  |  |  |  | mberens@leegov.com
Mandated
CW | 406713 | Master Signal Project/Major Intersections | Intersection conditions/ |  | 10460704 | 2628852 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 7500000 | 0 | 20589556 | GT | Dave Murphy 533-8578
|  | Funds for small-scale intersection improvements, including signalization | needs |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | dmurphy@leegov.com
NM - Core Critical
CW | 406079 | ADA Plan Implementation | Federal Law, ADA plan |  | 750794 | 499205 | 250000 | 250000 | 250000 | 250000 | 250000 | 1250000 | 0 | 2499999 | GT | Alejandro Slaibe, 533-8141
|  | Funds to make improvements on County roads per ADA Transition Plan | Mandated |  | DES,CST | CST | CST | CST | CST | CST | CST |  |  |  |  | aslaibe@leegov.com
CW |  | Roadway Lighting Upgrade | Sustainability, operating |  | 479537 | 870463 | 450000 | 0 | 0 | 450000 | 450000 | 1350000 | 0 | 2700000 | GT | Mike Padgett 533-9500
| 406080 | Funds to replace lighting fixtures with LED | cost reduction |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | mpadgett@leegov.com
NM - Core Critical
CW | 406714 | Signal Network | Age of current system, |  | 147340 | 200272 | 120000 | 120000 | 120000 | 120000 | 120000 | 600000 | 0 | 947612 | GT | Rob Radford, 533-0110
|  | Upgrade existing Traffic Signal Network | disaster recover/backup |  | CST |  | CST | CST | CST | CST | CST |  |  |  |  | rradford@leegov.com
|  | Traffic and Engineering Services | security
NM - Essential
CW | 406763 | Sign Replacement Program/Raised Pavement Markers | Sign conditions, safety, |  | 335848 | 208926 | 150000 | 150000 | 150000 | 150000 | 150000 | 750000 | 0 | 1294774 | GT | Dan Vasiloff, 533-9500
|  | Funds to keep County-owned traffic regulatory and informational signage | liability |  | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | dvasiloff@leegov.com
|  | up to standards | Mandated
1,2 | NEW | Traffic Signal Technology | Changing technologies |  | 0 | 500000 | 250000 | 250000 | 250000 | 250000 | 250000 | 1250000 | 0 | 1750000 | GT | Rob Price
|  | Study connected vehicle | [13 empty] | rprice@leegov.com
CW | 408944 | Overhead Sign Structures Evaluation | Maintenance obligations, |  | 85976 | 385248 | 130000 | 0 | 0 | 130000 | 130000 | 390000 | 0 | 861224 | GT | Mike Padgett 533-9500
|  | Funds to inspect 1/5 of overhead sign structures every year | liability, FDOT standards |  | Eval | CST | CST | CST | CST | CST | CST |  |  |  |  | mpadgett@leegov.com
Mandated
|  | SUBTOTALS |  |  | 80818369 | 20968236 | 13360000 | 13645000 | 12535000 | 13125000 | 13125000 | 65790000 | 0 | 154720094
|  | TOTAL |  |  | 203208246 | 155252272 | 89827987 | 76652852 | 101595588 | 76540308 | 21693367 | 366310102 | 284141510 | 1010060953
| NOTE: | Budget figures represent estimates for programming purposes. All dollar figures are subject to adjustment. Program year represents when funds are available, not necessarily when phase started or completed.
Totals exclude loan repayments/interest.
KEY (PHASES): |  | PRELIM = Preliminary Study; PD&E = Project Development & Environmental Study; DES = Design; ROW = Right-of-Way Acquisition; CST = Construction; CEI = Construction Engineering Inspection; PM = Project Management; LS = Landscaping;
MIT = Mitigation
KEY (FUNDS): |  | IF23 = Road Impact Fees from District 23; GT = Local Option Gas Taxes; CITY = City funds; PS = Public Safety funds; FDOT = Florida Dept. of Transportation; AV = Ad Valorem; GIF = Growth Increment Funding