## Bid Items
Form 1a – Bid/Proposal Form (not applicable for CCNA solicitations)
COUNTYWIDE RESURFACING ROADWAY IMPROVEMENT |  |  |  |  | Ver: 08/29/2017
CW LEHIGH ACRES LOCALS 2018-a (1-FY-2018-a) |  |  |  | Bid No: | B170431LKD
Contractor:
Having carefully examined the “Terms and Conditions”, and the “Detailed Scope of Work”, all of which are contained herein, propose to furnish the following which meet these specifications.
Term: From Notice to Proceed or Purchase Order date, whichever applies: 150 calendar days to substantial completion, 30 calendar days to final completion (total days 180).
Liquidated Damages: (Construction) Liquidated damages of $ 1,000 per calendar day(s) will be assessed to the contractor/vendor for each consecutive calendar day completion of the project or work is delayed.
Quantities are estimates. It is the bidders responsibility to field verify.
ITEM NO. | DESCRIPTION | UNIT | EST. | UNIT | TOTAL
|  |  | QTY. | PRICE
101-1 | Mobilization | LS | 1
102-1 | Maintenance of Traffic | LS | 1
120-1 | Roadway Excavation | SY | 1500
120-6 | Embankment | CY | 750
230-6 | Optional Base Group 6 | SY | 1500
280-1 | Asphalt Base Course III (Swale Leveling) | TN | 1500
327-1 | Milling of Existing Asphalt | SY | 500
330-10 | Asphalt Leveling Course | TN | 500
430-8 | 12" X 18" RCP - CD | FT | 2544
570-1 | Seeding / Mulching | SY | 200
575-1 | Sodding | SY | 200
331-1 | 1" Type S-3 Wearing Course | TN | 29391.8333
Grand Total:
Grand Total (written in words):
Addendum 1 B170431LKD Countywide Resurfacing Roadway Improvement Lehigh Acres Locals 2018-a (1-FY2018-a)

## Road Items
COUNTYWIDE RESURFACING ROADWAY IMPROVEMENT |  |  |  | ver: 07/13/2017
CW LEHIGH ACRES LOCALS 2018-a (1-FY-2018-a) |  |  |  | Bid No: | B170431LKD
Quantities are estimates. It is the bidders responsibility to field verify.
Contractor:
[7 empty] | Total |  |  | # Of
| StreetName | From | To | Wd Ft | Ln Ft | Tons | Asphalt $ |  |  | Swales
1 | OLIVE AVE S | 1st St SW | N EOP | 18 | 350 | 52.5 | 4462.5 | yes | 1 occ | 1
2 | 9TH ST SW | W EOP | Joan Ave S | 18 | 850 | 127.5 | 10837.5 |  |  | 0
3 | 6TH ST SW | W EOP | Joan Ave S | 18 | 430 | 64.5 | 5482.5 | n | 1 occ | 0
4 | 5TH ST SW | W EOP | Ida Ave S | 18 | 500 | 75 | 6375 |  |  | 0
5 | IDA AVE S | 1st St SW | N EOP | 18 | 300 | 45 | 3825 | no | 1 occ | 0
6 | HAZEL AVE S | 1st St SW | N EOP | 18 | 300 | 45 | 3825 | no | 2 occ | 1
7 | GENE AVE S | 1st St SW | N EOP | 18 | 300 | 45 | 3825 | no | 1 occ | 0
8 | FLORA AVE S | 1st St SW | N EOP | 18 | 300 | 45 | 3825 | no | 1 occ | 0
9 | 12TH ST SW | W EOP | Elva Ave S | 18 | 850 | 127.5 | 10837.5 | yes | 6 occ | 0
10 | ELVA AVE S | 17th St SW | 8th St SW | 18 | 2950 | 442.5 | 37612.5 | min coll |  | 0
11 | 22ND ST SW | W EOP | Connie Ave S | 18 | 480 | 72 | 6120 | no | 2 occ | 0
12 | 18TH ST SW | W EOP | CONNIE AVE S | 18 | 580 | 87 | 7395 | yes | 2 occ | 0
13 | BETH AVE S | 17th St SW | N EOP | 18 | 400 | 60 | 5100 | no | 1 occ | 1
14 | 17TH ST SW | Anita Ave SW | E EOP | 18 | 370 | 55.5 | 4717.5 | no | 1 occ | 0
15 | ANITA AVE S | 21st St SW | 17th St SW | 18 | 1300 | 195 | 16575 | yes | 0 occ | 9
16 | 21ST ST SW | Connie Ave S | E EOP | 18 | 900 | 135 | 11475 | yes | 1 occ | 0
17 | RUTH AVE S | 16th St SW | N EOP | 18 | 320 | 48 | 4080 | no | 1 occ | 0
18 | PEARL AVE S | 16th St SW | N EOP | 18 | 300 | 45 | 3825 | no | 1 occ | 0
18 | PAULA AVE S | 16TH St SW | N EOP | 18 | 270 | 40.5 | 3442.5 | no | 1 occ | 0
20 | OLIVE AVE S | 18th St SW | 16th St SW | 18 | 680 | 102 | 8670 | yes | min coll | 0
21 | SUSAN AVE S | 16th St SW | N EOP | 18 | 380 | 57 | 4845 |  |  | 0
22 | SUSAN AVE S | S EOP | 30th St SW | 18 | 200 | 30 | 2550 | no | 1 occ | 1
23 | SARA AVE S | 30th St SW | 26th St SW | 18 | 1400 | 210 | 17850 | yes | entr rd | 0
24 | 29TH ST SW | Sara Ave S | Rena Ave S | 18 | 850 | 127.5 | 10837.5 | 3 occ |  | 0
25 | 28TH ST SW | Sara Ave S | Rena Ave S | 18 | 850 | 127.5 | 10837.5 | no | 2 occ | 0
26 | OLIVE AVE S | S EOP | 30th St SW | 18 | 300 | 45 | 3825 | 1 occ |  | 0
27 | NORA AVE S | S EOP | 30th St SW | 18 | 350 | 52.5 | 4462.5 |  | 1 occ | 1
28 | 32ND ST SW | W EOP | Sunshine Ave S | 18 | 1100 | 165 | 14025 | 1 occ |  | 0
29 | PAULA AVE S | 32nd St SW | N EOP | 18 | 300 | 45 | 3825 | 2 occ |  | 1
30 | NORA AVE S | 34th St SW | 32nd St SW | 18 | 650 | 97.5 | 8287.5 | n | entr rd | 1
31 | 33RD ST SW | W EOP | Nora Ave S | 18 | 720 | 108 | 9180 | 2 occ |  | 0
32 | 38TH ST SW | W EOP | Sara Ave S | 18 | 900 | 135 | 11475 | 1 occ |  | 0
33 | 43RD ST SW | Sara Cir | Sally Ave S | 18 | 350 | 52.5 | 4462.5 | 1 occ |  | 1
34 | SALLY AVE S | Meadow Rd | 42nd St SW | 18 | 1000 | 150 | 12750 | 3 occ |  | 1
35 | 41ST ST SW | Ruth Ave S | W EOP | 18 | 850 | 127.5 | 10837.5 | 1 occ |  | 0
36 | NORA AVE S | 44th St SW | 41st St SW | 18 | 950 | 142.5 | 12112.5 | 1 occ |  | 1
37 | 42ND ST SW | Olive Ave S | Nora Ave S | 18 | 380 | 57 | 4845 | 2 occ |  | 1
38 | 43RD ST SW | Olive Ave S | Nora Ave S | 18 | 380 | 57 | 4845 | 1 occ |  | 0
39 | OLIVE AVE S | 47th St SW | 46th St SW | 18 | 300 | 45 | 3825 | no | 1 occ | 1
40 | LORAINE AVE S | 48th St SW | N EOP | 18 | 300 | 45 | 3825 | no | 1 occ | 1
41 | JOAN AVE S | 48th St SW | N EOP | 18 | 300 | 45 | 3825 | no | 1 occ | 1
42 | 48TH ST SW | W EOP | Irene Ave S | 18 | 1400 | 210 | 17850 | 2 occ |  | 0
43 | GENE AVE S | Meadow Rd | 52nd St SW | 18 | 700 | 105 | 8925 |  |  | 0
44 | 53RD ST SW | Gene Ave S | E EOP | 18 | 1650 | 247.5 | 21037.5 |  |  | 0
45 | 54TH ST SW | Elva Ave S | E EOP | 18 | 800 | 120 | 10200 | 4 occ |  | 2
46 | CONNIE AVE S | 40th St SW | 37th St SW | 18 | 1050 | 157.5 | 13387.5 |  |  | 0
47 | ANITA AVE S | 40th St SW | 38th St SW | 18 | 700 | 105 | 8925 |  |  | 0
48 | 41ST ST SW | Connie Ave S | E EOP | 18 | 800 | 120 | 10200 | 2 occ |  | 0
49 | PAGEANT ST | Pauline Ave | Palmyra Ave | 18 | 560 | 84 | 7140 | no | 1 occ | 1
50 | PEORIA ST | Perlita Ave | Paulcrest Ave | 18 | 560 | 84 | 7140 | 2 occ | 1 calls | 1
51 | PANORAMA AVE | Pageant St | Paddock St | 18 | 1150 | 172.5 | 14662.5 | no | 1 occ | 2
52 | PAXTON ST | Parkman Ave | Paulcrest Ave | 18 | 600 | 90 | 7650 | no | 2 occ | 0
53 | PARKMAN AVE | Paxton St | Pullman Ave | 18 | 660 | 99 | 8415 | no | 0 occ | 0
54 | PYRAMID AVE | Alabama Rd S | Patio St | 18 | 660 | 99 | 8415 | yes | min coll | 0
55 | PELHAM RD | Alabama Rd S | Peerless St | 18 | 1700 | 255 | 21675 | yes | min coll | 0
56 | PYRAMID AVE | Partridge St | Grant Blvd | 18 | 1000 | 150 | 12750 | yes | min coll | 0
57 | PARNELL AVE | Preston Ave | Grant Blvd | 18 | 800 | 120 | 10200 | no | 2 occ | 1
58 | PAULCREST AVE | Preston Ave | Grant Blvd | 18 | 900 | 135 | 11475 | no | 2 occ | 1
59 | PARTRIDGE ST | Pauline Ave | Palmyra Ave | 18 | 700 | 105 | 8925 | 1 occ | 2 calls | 0
60 | PEMBROKE ST | Milwaukee Blvd | Petite Ave | 18 | 400 | 60 | 5100 | yes | min coll | 0
61 | PARTRIDGE ST | Petite Ave | Pontoon Ave | 18 | 600 | 90 | 7650 | no | 1 occ | 1
62 | MILLCREEK ST | Aletha Ave S | Alabaster St | 18 | 1400 | 210 | 17850 | yes | 3 occ | 0
63 | HIGBY ST E | Homestead Rd S | Burns Ave S | 18 | 360 | 54 | 4590 | yes | entr rd | 0
64 | BURNS AVE S | Keller St E | Allison St E | 18 | 400 | 60 | 5100 | yes | min coll | 0
65 | RAINTREE ST E | Burns Ave S | Troy Ave S | 18 | 2200 | 330 | 28050 | yes | min coll | 0
66 | KINGSBURY LN | Thomas Sherwin Ave S | Theodore Vail St E | 18 | 2200 | 330 | 28050 | y | 10 occ | 1
67 | KILGOUR Ave S | Kingsbury Ln | Theodore Vail St E | 18 | 1280 | 192 | 16320 | y | 4 occ | 4
68 | LOTUS AVE S | Chemstrand St E | Grant Blvd | 18 | 1500 | 225 | 19125 | yes | 2 occ | 0
69 | BECKLEY DR | Ashland St E | Palmer St E | 18 | 2450 | 367.5 | 31237.5 | y | 6 occ | 0
70 | ELSA AVE S | Sentinela Blvd | Asther St E | 18 | 350 | 52.5 | 4462.5 | no | 0 occ | 1
71 | ASTHER ST E | Elsa Ave S | Grant Blvd | 18 | 1300 | 195 | 16575 | y | 2 occ | 1
72 | NACELLE CT | Sentinela Blvd | N EOP | 18 | 400 | 60 | 5100 | yes | 3 occ | 1
73 | OAR CT | Sentinela Blvd | N EOP | 18 | 400 | 60 | 5100 | yes | 2 occ | 1
74 | BINKLEY ST E | Aurora Ave S | Grant Blvd | 18 | 3900 | 585 | 49725 | yes | 2 occ | 1
75 | BOWMAN AVE S | Binkley St E | Alcade St E | 18 | 1250 | 187.5 | 15937.5 | yes | 3 occ | 0
76 | ALCALDE ST E | Aurora Ave S | Grant Blvd | 18 | 3900 | 585 | 49725 | yes | 3 occ | 1
77 | EUPHRATES AVE S | Alcade St E | Binkley St E | 18 | 1200 | 180 | 15300 | n | entr rd | 0
78 | CARROLL ST E | Callaway Ave S | Euphades Ave S | 18 | 1360 | 204 | 17340 | YES | 6 occ | 3
79 | CAMDEN ST E | Colbert Ave S | Euphades Ave S | 18 | 700 | 105 | 8925 | yes | 3 occ | 1
80 | NABOB AVE | Randolph St E | Randletree St E | 18 | 900 | 135 | 11475 | y | 2 occ | 1
81 | NARCISSUS AVE S | Randolph St E | Randletree St E | 18 | 850 | 127.5 | 10837.5 | y | 2 occ | 1
82 | NAUTILUS AVE S | Randolph St E | Randletree St E | 18 | 820 | 123 | 10455 | yes | 3 occ | 1
83 | CELTIC ST E | Malaree Ave S | Naples Ave S | 18 | 1280 | 192 | 16320 | y | 3 occ | 1
84 | LESTER AVE S | Catenary St E | Chrysler St E | 18 | 1050 | 157.5 | 13387.5 | y | entr rd | 0
85 | SUMMA BLVD | Columbus Blvd | Naples Ave S | 18 | 2200 | 330 | 28050 | yes | 8 occ | 0
86 | COUNTY ST E | Lambda Ave S | Naples Ave S | 18 | 1900 | 285 | 24225 | yes | 3 occ | 2
87 | COUNT ST E | Mallory Ave S | Naples Ave S | 18 | 900 | 135 | 11475 | y | 2 occ | 1
88 | NAPLES AVE S | Summa Blvd | Creary St E | 18 | 1000 | 150 | 12750 | no | 3 occ | 0
89 | CREARY ST E | Mallory Ave S | Naples Ave S | 18 | 900 | 135 | 11475 | no | 3 occ | 1
90 | MALLORY AVE S | Croquet St E | Summa Blvd | 18 | 1900 | 285 | 24225 | n | entr rd | 1
91 | LACONIC AVE S | Crestwood St E | Cummings St E | 18 | 650 | 97.5 | 8287.5 | yes | 3 occ | 0
92 | VALEVIEW AVE S | Grove St E | Summa Blvd | 18 | 1280 | 192 | 16320 | yes | entr rd | 0
93 | MERRY CT | Merry St E | N EOP | 18 | 300 | 45 | 3825 | yes |  | 0
94 | MERRY ST E | Eisenhower Blvd | Western Ave S | 18 | 3000 | 450 | 38250 | yes |  | 0
95 | GROVE ST E | Norwood Ave S | Western Ave S | 18 | 1550 | 232.5 | 19762.5 | y | 3 occ | 1
96 | BARNETT ST E | Eisenhower Blvd | Western Ave S | 18 | 2300 | 345 | 29325 | yes | 6 occ | 0
97 | KAYE ST E | Norwood Ave S | Western Ave S | 18 | 1300 | 195 | 16575 | y | 2 occ | 0
98 | WINDSOR AVE S | Kent St E | Kaye St E | 18 | 1000 | 150 | 12750 | yes | 2 occ | 2
99 | McARTHUR BLVD | Grant Blvd | Milwaukee Blvd | 20 | 4800 | 800 | 68000 | yes |  | 0
100 | REDWOOD AVE S | Macy St E | Hansen St E | 18 | 1900 | 285 | 24225 | yes | 2 occ | 2
101 | MACY ST E | Redwood Ave S | Summit Ave S | 18 | 650 | 97.5 | 8287.5 | yes | coll rd | 0
102 | HUNTER ST E | Redwood Ave S | Summit Ave S | 18 | 650 | 97.5 | 8287.5 | yes | 2 occ | 2
103 | MADDOCK ST E | Flamingo Ave | Parker Ave S | 18 | 1000 | 150 | 12750 | no | entr rd | 0
104 | CYPRESS AVE S | Kanuga St E | Maddock St E | 18 | 1400 | 210 | 17850 | yes | 3 occ | 1
105 | PARKER AVE | Kanuga St E | Milwaukee Blvd | 18 | 1600 | 240 | 20400 | yes | 2 occ | 0
106 | ASPEN AVE S | Kanuga St E | Winters St E | 18 | 600 | 90 | 7650 | y | 2 occ | 0
107 | WINTERS ST E | Parker Ave S | Aspen Ave S | 18 | 1750 | 262.5 | 22312.5 | yes | 2 occ | 1
108 | ARTIC ST E | Genoa Ave S | Barranger Ave S | 18 | 950 | 142.5 | 12112.5 | y | 2 occ | 1
109 | BARRANGER AVE S | Artic St E | Welland St E | 18 | 600 | 90 | 7650 | n | entr rd | 1
110 | HERRIN AVE S | Amherst St E | Augusta St E | 18 | 860 | 129 | 10965 | yes | 3 occ | 2
111 | FAIRFAX AVE S | Amherst St E | Augusta St E | 18 | 880 | 132 | 11220 | yes | 3 occ | 2
112 | MONTCLAIR AVE S | Amherst St E | Bayou St E | 18 | 650 | 97.5 | 8287.5 |  |  | 0
113 | BEAVER ST E | Montclair Ave S | Gumwood Ave S | 18 | 1000 | 150 | 12750 | y | 1 occ | 1
114 | GUMWOOD AVE S | Beaver St E | Bayou St E | 18 | 300 | 45 | 3825 | y | 1 occ | 0
115 | GUMWOOD AVE S | Belair St E | Hillburn St E | 18 | 300 | 45 | 3825 | y | 0 occ | 1
116 | MONTCLAIR AVE S | Boxwood St E | Milwaukee Blvd | 18 | 1400 | 210 | 17850 | yes | 3 occ | 1
117 | MOBLEY ST E | Columbus Blvd | Montclair Ave S | 18 | 380 | 57 | 4845 | no | entr rd | 2
118 | BOXWOOD ST E | Montclair Ave S | Naples Ave S | 18 | 1880 | 282 | 23970 | yes | 3 occ | 1
119 | GLENQUIST AVE S | Hudson St E | Boxwood St E | 18 | 1150 | 172.5 | 14662.5 | y | 3 occ | 2
120 | IVANHOE AVE S | Hudson St E | Boxwood St E | 18 | 1100 | 165 | 14025 | y | 1 occ | 2
121 | HUDSON ST E | Genoa Ave S | Columbus Blvd | 18 | 2350 | 352.5 | 29962.5 |  |  | 1
122 | STANLEY AVE S | Hudson St E | Jean St E | 18 | 1200 | 180 | 15300 | yes | 2 occ | 1
123 | APRILE AVE S | Jaguar Blvd | Venetia St E | 18 | 900 | 135 | 11475 | yes | 5 occ | 1
124 | PINECASTLE DR | Pine Cove Dr | Jaguar Blvd | 18 | 950 | 142.5 | 12112.5 | yes | 2 occ | 1
125 | DRUM CT | Pine Cove Dr | N EOP | 18 | 400 | 60 | 5100 | no | 1 occ | 0
126 | PINE COVE DR | Danforth St | Pinecastle Dr | 18 | 1800 | 270 | 22950 | yes | 3 occ | 1
127 | HORN CT | Pine Cove Dr | E EOP | 18 | 500 | 75 | 6375 | no | 1 occ | 1
128 | APPLETON AVE | Holmes Ave | Danforth St | 18 | 1200 | 180 | 15300 | yes | 2 occ | 2
129 | ASHLEY OAKS DR | Chenault St | Cold Water Ave | 18 | 1100 | 165 | 14025 | y | 2 occ | 0
130 | ARDMORE ST | Ashley Rd | Bedford Dr | 18 | 2300 | 345 | 29325 | yes | 2 occ | 4
131 | BEDFORD POINT AVE | Ardmore St | Bolivia Dr | 18 | 1250 | 187.5 | 15937.5 | yes | 2 occ | 0
132 | CANDLELIGHT DR | Holmes Ave | E EOP | 18 | 2500 | 375 | 31875 | yes | 7 occ | 3
133 | FOXDALE AVE | Nimitz Blvd | Garnet Ave | 18 | 1150 | 172.5 | 14662.5 | y | 3 occ | 0
134 | GARNET AVE | Fayette Ave | Nimitz Blvd | 18 | 1250 | 187.5 | 15937.5 | n | 3 occ | 1
135 | MANILA AVE S | Ebers St E | Earhart St E | 18 | 950 | 142.5 | 12112.5 | yes | 3 occ | 1
136 | EBERS ST E | Manresa Ave S | Manila Ave St | 18 | 830 | 124.5 | 10582.5 | yes | 3 occ | 1
137 | EBERT ST E | Manila Ave S | Manresa Ave S | 18 | 800 | 120 | 10200 | n | 4 occ | 2
138 | PARNELL CT | Kirkwood St | E EOP | 18 | 800 | 120 | 10200 | y | 2 occ | 0
139 | KIRKWOOD ST | Meadow Rd | Meadow Rd | 18 | 2600 | 390 | 33150 | y | 2 occ | 1
140 | MEADOW RD | Kirkwood St | Genoa Ave S | 20 | 1800 | 300 | 25500 | yes | coll rd | 0
141 | SHALLOWFORD ST | Eisenhower Blvd | Capetown Ave | 18 | 700 | 105 | 8925 | yes | entr rd | 1
142 | REDBANK AVE | Meadow Rd | Grafton St | 18 | 1050 | 157.5 | 13387.5 | yes | 1 occ | 1
143 | MOONBEAM ST | Meadow Rd | Redbank Ave | 18 | 900 | 135 | 11475 | y | 2 occ | 2
|  |  | TOTALS |  | 149640 | 22556 | 1917260 |  |  | 106
28.3409

## Addendum 1 Added Roads
COUNTYWIDE RESURFACING ROADWAY IMPROVEMENT
CW LEHIGH ACRES LOCALS 2017a |  |  | Addendum to 1-FY/2018a
| 1-FY-2018-Addendum Roads |  | Bid No:
| STREET NAME | FROM | TO | W | L | TONS
Add-1-1 | MILWAUKEE BLVD | Bell Blvd | Columbus Blvd | 22 | 10500 | 1925
Add-1-2 | W 17TH ST | Lee Ave | Richmond Ave N | 22 | 12700 | 2328.3333
Add-1-3 | GREENBRIAR BLVD | Richmond Ave | Roderick Ln | 20 | 5100 | 850
Add-1-4 | TREMAINE ST | Laurie St | Richmond Ave N | 18 | 1275 | 191.25
Add-1-5 | LODGE ST | Tremaine St | McClure | 18 | 1000 | 150
Add-1-6 | E 16TH ST | Joel Blvd | Leroy Ave | 18 | 6400 | 960
Add-1-7 | TRUMAN AVE | E 16th St | E 17th St | 18 | 1600 | 240
Add-1-8 | STATE AVE | W 11th St | W 12th St | 18 | 1275 | 191.25
6835.8333
Addendum 1 B170431LKD Countywide Resurfacing Roadway Improvement Lehigh Acres Locals 2018-a (1-FY2018-a)