## 3 Oaks BID-PROPOSAL FORM
PROCUREMENT MANAGEMENT BID SCHEDULE
COMPANY NAME:
SOLICITATION: | B240349DWJ - Three Oaks WRF DIW-2
Having carefully examined the Contract Documents, Contractor/Vendor proposes to furnish the following which meeting these specifications.
PRICING Pricing shall be inclusive of all labor, equipment, supplies, overhead, profit, material, and any other incidental costs required to perform and complete all work as specified in the Contract Documents. All Unit Prices will be bid at the nearest whole penny. The Excel document contains formulas for convenience, however it is the Contractor’s/Vendor's responsibility to verify all pricing and calculations are CORRECT. Lee County is not responsible for errors in formulas or calculations contained within Excel document(s). In the event there is a discrepancy between a subtotal or total amount and the unit prices and extended amounts, the unit prices will prevail and the corrected extension(s) and total(s) will be considered the price. The County will only accept bids submitted on bid forms provided by the County. Bids submitted on other forms, other than those provided by the County, will be deemed non-responsive and ineligible for award. PLEASE ENSURE you have provided a printed copy of the Bid Schedule with your hard copy submission packages and provided the excel version with your digital submission package.
THREE OAKS DEEP INJECTION WELL #2
PART 1 - DOWNHOLE CONSTRUCTION
GENERAL
Item | Description | Unit of Measure | Estimated Quantity | Unit Price | Extended Amount
I-1 | General requirements, or Home/Field Office Overhead as delineated in the general and supplemental conditions including Division 01 of the Contract | LS | 1 |  | 0
I-2 | Mobilization and site preparation for injection well (includes temporary power and permitting). | LS | 1 |  | 0
I-3 | Demobilization from the injection well, performing final grading once the well is constructed and clean up, including as-built survey | LS | 1 |  | 0
I-4 | Loss Circulation Zone Gravel Contingency | CF | 1500 |  | 0
I-5 | Stand-By Time // Drill Rig and Crew ( Stand-By paid max 12 hours/day) | HR | 2000 |  | 0
SUBTOTAL: |  |  |  |  | 0
INJECTION WELL
Item | Description | Unit of Measure | Estimated Quantity | Unit Price | Extended Amount
II-1 | Construct concrete or steel drilling pad | LS | 1 |  | 0
II-2 | Construct water table monitoring wells | EA | 4 |  | 0
II-3 | Collection and analysis reports of weekly water quality samples from monitoring wells | LS | 1 |  | 0
II-4 | Furnish and install 54-inch diameter pit steel casing | LS | 1 |  | 0
II-5 | Drill a 12.25‐inch diameter pilot hole to approximately 515 feet bls | LF | 515 |  | 0
II-6 | Perform geophysical logging to approximately 515 feet bls | LS | 1 |  | 0
II-7 | Ream a nominal 52‐inch diameter borehole to approximately 490 feet bls | LF | 490 |  | 0
II-8 | Perform geophysical logging to 490 feet bls | LS | 1 |  | 0
II-9 | Deliver 44-inch diameter surface steel casing | LF | 490 |  | 0
II-10 | Install 44-inch diameter surface steel casing | LS | 1 |  | 0
II-11 | Furnish and install cement for the 44-inch diameter surface steel casing | CF | 2592 |  | 0
II-12 | Install flow prevention device and transition to reverse-air drilling techniques | LS | 1 |  | 0
II-13 | Drill a 12.25‐inch diameter pilot hole (490 feet to 1,425 feet bls) | LF | 935 |  | 0
II-14 | Drill and collect rock cores between approximately 490 feet to 1,425 feet bls | EA | 4 |  | 0
II-15 | Laboratory analysis for rock cores between approximately 490 feet to 1,425 feet bls | EA | 8 |  | 0
II-16 | Perform static and dynamic geophysical logging from approximately 490 feet to 1,425 feet bls | LS | 1 |  | 0
II-17 | Perform packer testing and water quality laboratory analysis between approximately 490 feet to 1,425 feet bls | EA | 4 |  | 0
II-18 | Backplug 12.25‐inch diameter pilot hole with cement (490 feet to 1,425 feet bls) | CF | 957 |  | 0
II-19 | Ream a nominal 42‐inch diameter borehole to approximately 1,400 feet bls | LF | 910 |  | 0
II-20 | Perform geophysical logging from approximately 490 feet to 1,400 feet bls | LS | 1 |  | 0
II-21 | Deliver 34-inch diameter intermediate steel casing | LF | 1400 |  | 0
II-22 | Install 34-inch diameter intermediate steel casing | LS | 1 |  | 0
II-23 | Furnish and install cement for 34-inch diameter intermediate steel casing | CF | 6088 |  | 0
II-24 | Perform geophysical logging associated with 34-inch steel casing installation | LS | 1 |  | 0
II-25 | Drill 12.25‐inch diameter pilot hole (1,400 feet to 2,150 feet bls) | LF | 750 |  | 0
II-26 | Drill and collect rock cores from approximately 1,400 feet to 2,150 feet bls | EA | 4 |  | 0
II-27 | Laboratory analysis for rock cores between approximately 1,400 feet to 2,150 feet bls | EA | 8 |  | 0
II-28 | Perform static and dynamic geophysical logging from approximately 1,400 feet to 2,150 feet bls | LS | 1 |  | 0
II-29 | Perform packer testing and water quality laboratory analysis from approximately 1,400 feet to 2,150 feet bls | EA | 4 |  | 0
II-30 | If required, install a drillable bridge plug at approximately 2,125 feet bls | EA | 1 |  | 0
II-31 | Backplug 12.25‐inch diameter pilot hole with cement (1,400 feet to 2,125 feet bls) | CF | 768 |  | 0
II-32 | Ream a nominal 32‐inch diameter borehole to approximately 2,100 feet bls | LF | 700 |  | 0
II-33 | Perform geophysical logging from approximately 1,400 feet to 2,100 feet bls | LS | 1 |  | 0
II-34 | Deliver 24-inch diameter final seamless steel casing | LF | 2100 |  | 0
II-35 | Install 24-inch diameter final seamless steel casing | LS | 1 |  | 0
II-36 | Furnish and install cement for the 24-inch diameter final seamless steel casing | CF | 7035 |  | 0
II-37 | Perform geophsyical logging associated 24-inch diameter final seamless steel casing | LS | 1 |  | 0
II-38 | Ream a nominal 22‐inch diameter borehole to approximately 2,860 feet bls | LF | 760 |  | 0
II-39 | Perform geophysical logging from approximately 2,100 feet to 2,860 feet bls | LS | 1 |  | 0
II-40 | Well development laboratory analysis / reporting of injection zone water quality samples | LS | 1 |  | 0
II-41 | Conduct internal and external MIT of the 24-inch diameter final seamless steel casing | LS | 1 |  | 0
II-42 | Short term injection test | LS | 1 |  | 0
SUBTOTAL: |  |  |  |  | 0
PART 1 - DOWNHOLE CONSTRUCTION TOTAL |  |  |  | 0
PART 2 - ABOVE SURFACE FACILITIES
Item | Description | Unit of Measure | Estimated Quantity | Unit Price | Extended Amount
III-1 | Mobilization, demobilization, survey, insurance, audio-video tape of existing conditions, preparing a field office, securing a staging area, and other adminstrative charges outlined in the Contract Documents. | LS | 1 |  | 0
III-2 | Furnish and install new concrete well pad for IW-2. | LS | 1 |  | 0
III-3 | Furnish and install DI IW-2 piping. | LF | 60 |  | 0
III-4 | Furnish and install SS IW-2 piping. | LF | 10 |  | 0
III-5 | Furnish and install gate valves. | EA | 5 |  | 0
III-6 | Furnish and install air valves. | EA | 2 |  | 0
III-7 | Furnish and install flow meters. | EA | 1 |  | 0
III-8 | Furnish and install concrete pipe supports. | EA | 3 |  | 0
III-9 | Furnish and install PVC drain line. | LF | 215 |  | 0
III-10 | Furnish and install electrical and instrumentation improvements (including MOV for 80-FCV-7). | LS | 1 |  | 0
III-11 | Finish grading and site resotoration. | LS | 1 |  | 0
SUBTOTAL: |  |  |  |  | 0
PART 2 - ABOVE SURFACE FACILITIES TOTAL |  |  |  | 0
BID SUMMARY
PROJECT TOTAL |  |  |  | 0
**Quantities are not guaranteed. Final payment will be based on actual quantities.
PROJECT TOTAL:
(Use Words to Write Total)

## BID-PROPOSAL FORM_JD (hidden)
PROCUREMENT MANAGEMENT DEPARTMENT ENGINEER'S ESTIMATE
COMPANY NAME:
SOLICITATION:
Having carefully examined the Contract Documents, Contractor/Vendor proposes to furnish the following which meeting these specifications.
PRICING Pricing shall be inclusive of all labor, equipment, supplies, overhead, profit, material, and any other incidental costs required to perform and complete all work as specified in the Contract Documents. All Unit Prices will be bid at the nearest whole penny. The Excel document contains formulas for convenience, however it is the Contractor’s/Vendor's responsibility to verify all pricing and calculations are CORRECT. Lee County is not responsible for errors in formulas or calculations contained within Excel document(s). In the event there is a discrepancy between a subtotal or total amount and the unit prices and extended amounts, the unit prices will prevail and the corrected extension(s) and total(s) will be considered the price. The County will only accept bids submitted on bid forms provided by the County. Bids submitted on other forms, other than those provided by the County, will be deemed non-responsive and ineligible for award. PLEASE ENSURE you have provided a printed copy of the Bid Schedule with your hard copy submission packages and provided the excel version with your digital submission package.
THREE OAKS DEEP INJECTION WELL #2 - CIP XXXX | [5 empty] | Pending CIP number
GENERAL
Item | Description | Unit of Measure | Estimated Quantity | Unit Price | Extended Amount
I-1 | General requirements, or Home Field Office Overhead as delineated in the general and supplemental conditions including Division 01 of the Contract | LS | 1 |  | 0
I-2 | Mobilization and site preparation for injection well (includes temproary power and permitting). | LS | 1 |  | 0
I-3 | Demobilization and clean up | LS | 1 |  | 0
I-4 | Loss Circulation Zone Gravel Contingency | CF | 1000 |  | 0 | Is this a standard number?
I-5 | Stand-By Time Drill Rig Only (max 12 hours/day) | HR | 75 |  | 0
I-6 | Stand-By Time Drill Rig and Crew (max 12 hours/day) | HR | 75 |  | 0
I-7 | Unforeseen Geologic Conditions - Stand-By Rate Drill Rig On-Site (24 hours/day) | HR | 720 |  | 0
I-8 | Unforeseen Geologic Conditions - Stand-By Rate Drill Rig Not On-Site (max 12 hours/day) | HR | 360 |  | 0
SUBTOTAL: GENERAL |  |  |  |  | 0
INJECTION WELL
Item | Description | Unit of Measure | Estimated Quantity | Unit Price | Extended Amount
II-1 | Construction of concrete or steel drilling pad | LS | 1 |  | 0
II-2 | Construction of water table monitoring wells | EA | 4 |  | 0
II-3 | Collection and analysis reports of water quality from monitoring wells | LS | 1 |  | 0
II-4 | Furnishing and installing 54-inch diameter pit casing | LS | 1 |  | 0
II-5 | Drilling a nominal 12.25‐inch diameter pilot hole to 515 feet bls | LF | 515 |  | 0
II-6 | Perform geophysical logging to 515 feet bls | LS | 1 |  | 0
II-7 | Reaming a nominal 52‐inch diameter borehole | LF | 490 |  | 0
II-8 | Perform geophysical logging to 490 feet bls | LS | 1 |  | 0
II-9 | Delivering 44-inch diameter steel casing | LF | 490 |  | 0
II-10 | Installation of the 44-inch diameter steel casing | LS | 1 |  | 0
II-11 | Furnish and install cement for the 44-inch diameter steel casing | CF | 2657.5 |  | 0 | See workbook calculations | 2592
II-12 | Perform geophysical logging associated with 44-inch steel casing | LS | 1 |  | 0
II-13 | Installation of flow prevention device / reverse-air drilling techniques | LS | 1 |  | 0
II-14 | Drilling a nominal 12.25‐inch diameter pilot hole (490 feet to 1,425 feet bls) | LF | 935 |  | 0
II-15 | Drilling and collecting formation core between 490 feet to 1,425 feet bls | EA | 4 |  | 0 | Let me know if it should say instead: collect cores between 1,000 and 1,425 feet bls
II-16 | Laboratory analysis for rock cores between 490 feet to 1,425 feet bls | EA | 8 |  | 0 | same as above
II-17 | Perform geophysical logging from 490 feet to 1,425 feet bls | LS | 1 |  | 0
II-18 | Perform packer testing and analysis between 490 feet to 1,425 feet bls | EA | 4 |  | 0
II-19 | Backplugging nominal 12.25‐inch diameter pilot hole (490 feet to 1,425 feet bls) | CF | 956.25 |  | 0 | See workbook calculations | 957
II-20 | Reaming a nominal 42‐inch diameter borehole | LF | 910 |  | 0
II-21 | Perform geophysical logging from 490 feet to 1,400 feet bls. | LS | 1 |  | 0
II-22 | Delivering 34-inch diameter steel casing | LF | 1400 |  | 0
II-23 | Installation of the 34-inch diameter steel casing | LS | 1 |  | 0
II-24 | Furnish and install cement for the 34-inch diameter steel casing | CF | 6147 |  | 0 | See workbook calculations | 6088
II-25 | Perform geophysical logging associated with 34-inch steel casing | LS | 1 |  | 0
II-26 | Drilling a nominal 12.25‐inch diameter pilot hole (1,400 feet to 2,150 feet bls) | LF | 750 |  | 0
II-27 | Drilling and collecting formation cores from 1,400 feet to 2,150 feet bls | EA | 4 |  | 0
II-28 | Laboratory analysis for rock cores between 1,400 feet to 2,150 feet bls | EA | 8 |  | 0
II-29 | Perform geophysical logging from 1,400 feet to 2,150 feet bls | LS | 1 |  | 0
II-30 | Perform packer testing and analysis from 1,400 feet to 2,150 feet bls | EA | 4 |  | 0
II-31 | Backplugging nominal 12.25‐inch dia pilot hole (1,400 feet to 2,150 feet bls) | CF | 766.25 |  | 0 | See workbook calculations | 742 | considering bridgeplug
II-32 | Reaming a nominal 32‐inch diameter borehole | LF | 700 |  | 0 |  | 766 | without bridgeplug
II-33 | Perform geophysical logging from 1,400 feet to 2,100 feet bls | LS | 1 |  | 0
II-34 | Delivering 24-inch final seamless steel casing | LF | 2100 |  | 0
II-35 | Installation of the 24-inch final seamless steel casing | LS | 1 |  | 0
II-36 | Furnish and install cement for the 24-inch final steel casing | CF | 7069.4 |  | 0 | See workbook calculations | 7035
II-37 | Perform geophsyical logging associated 24-inch final steel casing | LS | 1 |  | 0 |  | 7069.4 | using workbook
II-38 | Reaming a nominal 22‐inch diameter borehole | LF | 760 |  | 0
II-39 | Perform geophysical logging from 2,100 feet to 2,860 feet bls | LS | 1 |  | 0
II-40 | Well development analysis / reporting of injection zone water samples | LS | 1 |  | 0
II-41 | Conduct internal and external MIT of the 24-inch final steel casing | LS | 1 |  | 0
II-42 | Short term injection test | LS | 1 |  | 0
SUBTOTAL: INJECTION WELL |  |  |  |  | 0
BID SUMMARY
PROJECT TOTAL |  |  |  | 0
**Quantities are not guaranteed. Final payment will be based on actual quantities.
PROJECT TOTAL:
(Use Words to Write Total)

## Cement Volumes
| Top (Ft) | Bottom (Ft) | Lift (Ft) | Diameter 1 (in) | Diameter 2 (in) | Volume (bbls) | Volume (Cubic Feet)
Surface Casing | 0 | 490 | 490 | 52 | 44 | 365.5722 | 2052.5355
Rathole | 490 | 515 | 25 | 12.25 |  | 3.6444 | 20.4619
[6 empty] | 100% | 2072.9973
[6 empty] | 125% | 2591.2467
| Top (Ft) | Bottom (Ft) | Lift (Ft) | Diameter 1 (in) | Diameter 2 (in) | Volume (bbls) | Volume (Cubic Feet)
Backplug | 490 | 1425 | 935 | 12.25 |  | 136.3012 | 765.2743
[6 empty] | 125% | 956.5929
| Top (Ft) | Bottom (Ft) | Lift (Ft) | Diameter 1 (in) | Diameter 2 (in) | Volume (bbls) | Volume (Cubic Feet)
Intermediate Casing (Cased Hole) | 0 | 490 | 490 | 43 | 34 | 329.8718 | 1852.0925
Intermediate Casing (Open Hole) | 490 | 1400 | 910 | 42 | 34 | 537.4781 | 3017.7158
Rathole | [5 empty] | 0 | -
[6 empty] | 100% | 4869.8084
[6 empty] | 125% | 6087.2605
| Top (Ft) | Bottom (Ft) | Lift (Ft) | Diameter 1 (in) | Diameter 2 (in) | Volume (bbls) | Volume (Cubic Feet)
Backplug | 1400 | 2150 | 750 | 12.25 |  | 109.3325 | 613.8564
[6 empty] | 125% | 767.3205
| Top (Ft) | Bottom (Ft) | Lift (Ft) | Diameter 1 (in) | Diameter 2 (in) | Volume (bbls) | Volume (Cubic Feet)
Final Casing (Cased Hole) | 0 | 1400 | 1400 | 33 | 24 | 697.688 | 3917.2273
Final Casing (Open Hole) | 1400 | 2100 | 700 | 32 | 24 | 304.6435 | 1710.4462
Rathole | [6 empty] | -
[6 empty] | 100% | 5627.6735
[6 empty] | 125% | 7034.5919